## MANPOWER LIST
SL NO: | NAME OF THE EMPLOYEE: | CURRENT DESIGNATION:
1 | AMAL K ANIL | QC/ENG
2 | RAHUL GIREESH | SUPERVISOR
3 | SELLAMUTHU RAVICHANDRAN | FITTER
4 | RAJAN YADAV | LAMINATOR
5 | BIJAY SADA | LAMINATOR
6 | GOVIND RAJ BAHAR | LAMINATOR
7 | RAJ BHAVAN YADAV | LAMINATOR
8 | GANGARAM POTHARLA | LAMINATOR
9 | VINOD PENTA | LAMINATOR
10 | VINEETH TIWARI | LAMINATOR

## DAILY PROGRESS
DAILY PROGRESS
DATE | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30
Planned(Yard) | 30 | 30 | 60 | 60 | 60 | 60
Planned(Site) | 30 | 30 | 0 | 0 | 0 | 0
Total | 60 | 60 | 60 | 60 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Lamination/Coupling
FW 4" | 0 | 0 | 0 | 0 | 0 | 0
FW 6" | 0 | 0 | 0 | 0 | 0 | 0
FW 8" | 0 | 0 | 0 | 0 | 0 | 0
FW 12" | 12 | 24 | 12 | 0 | 0 | 0
PW 12" | 0 | 0 | 0 | 24 | 24 | 0
DW 2" | 0 | 0 | 0 | 0 | 0 | 0
DW 3" | 0 | 0 | 0 | 0 | 0 | 0
D 3" | 0 | 0 | 0 | 0 | 0 | 0
D 4" | 0 | 12 | 28 | 0 | 0 | 28
D 6" | 0 | 0 | 0 | 0 | 0 | 0
AOC 20" | 0 | 0 | 0 | 0 | 0 | 0
TOTAL DIA INCH COMPLETED | 12 | 36 | 40 | 24 | 24 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Variance | -48 | -24 | -20 | -36 | -36 | -32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FITUP AND LAMINATION,COUPLING | [9 empty] | FITUP ONLY
|  | SIZE | TOTAL COMPLETED DIA INCH TILL NOW | [8 empty] | SIZE | TOTAL COMPLETED DIA INCH TILL NOW
|  | FW 4" | 40 | [8 empty] | FW 4" | 40
|  | FW 6" | 60 | [8 empty] | FW 6" | 78
|  | FW 8" | 176 | [8 empty] | FW 8" | 168
|  | FW 12" | 324 | [8 empty] | FW 12" | 336
|  | PW 12" | 48 | [8 empty] | PW 12" | 48
|  | DW 2" | 0 | [8 empty] | DW 2" | 0
|  | DW 3" | 0 | [8 empty] | DW 3" | 0
|  | D 3" | 0 | [8 empty] | D 3" | 0
|  | D 4" | 1012 | [8 empty] | D 4" | 1040
|  | D 6" | 0 | [8 empty] | D 6" | 0
|  | AOC 20" | 120 | [8 empty] | AOC 20" | 120
|  | TOTAL DIA INCH COMPLETED |  |  | 1780 | [6 empty] | TOTAL DIA INCH COMPLETED |  |  | 1830

## DAILY WORK REPORT
JOINT REPORT
SL.NO | Date | Service | Unit | Line | Train | Joint | JointType | Location | JointSize | MANPOWER AT SITE | REASON FOR DELAY
1 | 2026-03-17 | FW | 58 | CN007UFW2453-1 | 001 | SW01 | CUTTING AND PREPARATION | SW | 6 | 5 | CUTTING AND PREPARATION COMPLETED FITUP AND LAMINATION ACTIVITY NOT STARTED DUE TO THE ABSENCE OF ADPF SUPERVISOR
2 | 2026-03-17 | FW | 58 | CN007UFW2453-1 | 001 | SW02 | CUTTING AND PREPARATION | SW | 6
3 | 2026-03-17 | FW | 58 | CN007UFW2453-1 | 001 | SW03 | CUTTING AND PREPARATION | SW | 6
4 | 2026-03-17 | FW | 58 | CN006UFW2365-1 | 001 | SW01 | CUTTING AND PREPARATION | SW | 6
5 | 2026-03-17 | FW | 58 | CN006UFW2365-1 | 001 | SW02 | CUTTING AND PREPARATION | SW | 6
6 | 2026-03-17 | FW | 58 | CN006UFW2365-1 | 001 | SW03 | CUTTING AND PREPARATION | SW | 6
7 | 2026-03-18 | FW | 58 | CN002UFW2442-1 | 001 | SW01 | CUTTING AND PREPARATION | SW | 6 | 5
8 | 2026-03-18 | FW | 58 | CN002UFW2442-1 | 001 | SW02 | CUTTING AND PREPARATION | SW | 6
9 | 2026-03-18 | FW | 58 | CN002UFW2442-2 | 002 | SW01 | CUTTING AND PREPARATION | SW | 6
10 | 2026-03-18 | FW | 58 | CN002UFW2442-2 | 002 | SW02 | CUTTING AND PREPARATION | SW | 6
11 | 2026-03-18 | FW | 58 | CN002UFW2442-2 | 002 | SW03 | CUTTING AND PREPARATION | SW | 6
12 | 2026-03-23 | FW | 58 | CN002UFW2447-1 | 001 | SW01 | CUTTING AND PREPARATION | SW | 6 | 5
13 | 2026-03-23 | FW | 58 | CN002UFW2447-1 | 001 | SW02 | CUTTING AND PREPARATION | SW | 6
14 | 2026-03-23 | FW | 58 | CN002UFW2447-1 | 001 | SW03 | CUTTING AND PREPARATION | SW | 6
15 | 2026-03-25 | FW | 58 | CN006UFW2525-1 | 001 | SW01 | CUTTING AND PREPARATION | SW | 4 | 8
16 | 2026-03-25 | FW | 58 | CN006UFW2525-1 | 001 | SW02 | CUTTING AND PREPARATION | SW | 4
17 | 2026-03-25 | FW | 58 | CN006UFW2525-1 | 001 | SW03 | CUTTING AND PREPARATION | SW | 4
18 | 2026-03-25 | FW | 58 | CN006UFW2525-1 | 001 | SW04 | CUTTING AND PREPARATION | SW | 4
19 | 2026-03-25 | FW | 58 | CN006UFW2525-1 | 001 | SW05 | CUTTING AND PREPARATION | SW | 4
20 | 2026-03-25 | FW | 58 | CN006UFW2525-1 | 001 | SW06 | CUTTING AND PREPARATION | SW | 4
21 | 2026-03-25 | FW | 58 | CN006UFW2525-1 | 001 | SW07 | CUTTING AND PREPARATION | SW | 4
22 | 2026-03-25 | FW | 58 | CN006UFW2525-1 | 001 | SW08 | CUTTING AND PREPARATION | SW | 4
23 | 2026-03-25 | FW | 58 | CN006UFW2525-1 | 001 | SW09 | CUTTING AND PREPARATION | SW | 4
24 | 2026-03-25 | FW | 58 | CN006UFW2525-1 | 001 | SW10 | CUTTING AND PREPARATION | SW | 4
25 | 2026-03-25 | FW | 58 | CN006UFW2525-1 | 001 | SW11 | CUTTING AND PREPARATION | SW | 4
26 | 2026-03-25 | FW | 58 | CN006UFW2525-1 | 001 | SW12 | CUTTING AND PREPARATION | SW | 4
27 | 2026-03-25 | FW | 58 | CN006UFW2525-1 | 001 | SW13 | CUTTING AND PREPARATION | SW | 4
28 | 2026-03-26 | D | 58 | CN002UD6955-3 | 003 | FW01 | CUTTING AND PREPARATION | FW | 4 | 8
29 | 2026-03-26 | D | 58 | CN002UD6955-3 | 003 | SW02 | CUTTING AND PREPARATION | SW | 4
30 | 2026-03-26 | D | 58 | CN002UD6955-3 | 003 | FW03 | CUTTING AND PREPARATION | FW | 4
31 | 2026-03-26 | FW | 58 | CN006UFW2525-1 | 001 | SW01 | CUTTING AND PREPARATION | SW | 4
32 | 2026-03-26 | FW | 58 | CN006UFW2525-1 | 001 | SW02 | CUTTING AND PREPARATION | SW | 4
33 | 2026-03-26 | FW | 58 | CN006UFW2525-1 | 001 | SW03 | CUTTING AND PREPARATION | SW | 4
34 | 2026-03-26 | FW | 58 | CN006UFW2525-1 | 001 | FW04 | CUTTING AND PREPARATION | FW | 4
35 | 2026-03-26 | FW | 58 | CN006UFW2525-1 | 001 | SW05 | CUTTING AND PREPARATION | SW | 4
36 | 2026-03-26 | FW | 58 | CN006UFW2525-1 | 001 | SW06 | CUTTING AND PREPARATION | SW | 4
37 | 2026-03-26 | FW | 58 | CN006UFW2525-1 | 001 | SW07 | CUTTING AND PREPARATION | SW | 4
38 | 2026-03-26 | FW | 58 | CN006UFW2525-1 | 001 | FW08 | CUTTING AND PREPARATION | FW | 4
39 | 2026-03-26 | FW | 58 | CN006UFW2525-1 | 001 | FW09 | CUTTING AND PREPARATION | FW | 4
40 | 2026-03-26 | FW | 58 | CN006UFW2525-1 | 001 | SW10 | CUTTING AND PREPARATION | SW | 4
41 | 2026-03-26 | FW | 58 | CN006UFW2525-1 | 001 | SW11 | CUTTING AND PREPARATION | SW | 4
42 | 2026-03-26 | FW | 58 | CN006UFW2525-1 | 001 | SW12 | CUTTING AND PREPARATION | SW | 4
43 | 2026-03-26 | FW | 58 | CN006UFW2525-1 | 001 | SW13 | CUTTING AND PREPARATION | SW | 4
44 | 2026-03-26 | D | 58 | CN002UD6955-1 | 001 | FW01 | CUTTING AND PREPARATION | FW | 4
45 | 2026-03-26 | D | 58 | CN002UD6955-1 | 001 | SW02 | CUTTING AND PREPARATION | SW | 4
46 | 2026-03-26 | D | 58 | CN002UD6955-1 | 001 | SW03 | CUTTING AND PREPARATION | SW | 4
47 | 2026-03-26 | D | 58 | CN002UD6955-1 | 001 | SW04 | CUTTING AND PREPARATION | SW | 4
48 | 2026-03-26 | D | 58 | CN002UD6955-1 | 001 | FW05 | CUTTING AND PREPARATION | FW | 4
49 | 2026-03-26 | D | 58 | CN002UD6955-1 | 001 | SW06 | CUTTING AND PREPARATION | SW | 4
50 | 2026-03-26 | D | 58 | CN002UD6955-1 | 001 | FW07 | CUTTING AND PREPARATION | FW | 4
51 | 2026-03-26 | D | 58 | CN002UD6955-1 | 001 | SW08 | CUTTING AND PREPARATION | SW | 4
52 | 2026-03-26 | D | 58 | CN002UD6955-1 | 001 | FW09 | CUTTING AND PREPARATION | FW | 4
53 | 2026-03-26 | D | 58 | CN002UD6955-4 | 004 | SW01 | CUTTING AND PREPARATION | SW | 4
54 | 2026-03-26 | D | 58 | CN002UD6955-4 | 004 | SW02 | CUTTING AND PREPARATION | SW | 4
55 | 2026-03-26 | D | 58 | CN002UD6955-6 | 006 | SW01 | CUTTING AND PREPARATION | SW | 4
56 | 2026-03-26 | D | 58 | CN002UD6955-6 | 006 | SW02 | CUTTING AND PREPARATION | SW | 4
57 | 2026-03-26 | D | 58 | CN002UD6955-6 | 006 | SW03 | CUTTING AND PREPARATION | SW | 4
58 | 2026-03-26 | D | 58 | CN002UD6955-6 | 006 | SW04 | CUTTING AND PREPARATION | SW | 4
59 | 2026-03-26 | D | 58 | CN002UD6955-6 | 006 | SW05 | CUTTING AND PREPARATION | SW | 4
60 | 2026-03-26 | D | 58 | CN002UD6955-6 | 006 | SW06 | CUTTING AND PREPARATION | SW | 4
61 | 2026-03-26 | D | 58 | CN002UD6955-6 | 006 | SW07 | CUTTING AND PREPARATION | SW | 4
62 | 2026-03-26 | D | 58 | CN002UD6955-6 | 006 | SW08 | CUTTING AND PREPARATION | SW | 4
63 | 2026-03-26 | D | 58 | CN002UD6955-6 | 006 | SW09 | CUTTING AND PREPARATION | SW | 4
64 | 2026-03-26 | D | 58 | CN002UD6955-6 | 006 | SW10 | CUTTING AND PREPARATION | SW | 4
65 | 2026-03-26 | D | 58 | CN002UD6955-6 | 006 | FW11 | CUTTING AND PREPARATION | FW | 4
66 | 2026-03-26 | D | 58 | CN002UD6982-2 | 002 | FW01 | CUTTING AND PREPARATION | FW | 4
67 | 2026-03-26 | D | 58 | CN002UD6982-2 | 002 | SW02 | CUTTING AND PREPARATION | SW | 4
68 | 2026-03-26 | D | 58 | CN002UD6982-2 | 002 | SW03 | CUTTING AND PREPARATION | SW | 4
69 | 2026-03-26 | D | 58 | CN002UD6982-2 | 002 | SW04 | CUTTING AND PREPARATION | SW | 4
70 | 2026-03-26 | D | 58 | CN002UD6982-2 | 002 | FW05 | CUTTING AND PREPARATION | FW | 4
71 | 2026-03-26 | D | 58 | CN002UD6982-2 | 002 | SW06 | CUTTING AND PREPARATION | SW | 4
72 | 2026-03-26 | D | 58 | CN002UD6982-2 | 002 | SW07 | CUTTING AND PREPARATION | SW | 4
73 | 2026-03-26 | D | 58 | CN002UD6982-2 | 002 | SW08 | CUTTING AND PREPARATION | SW | 4
74 | 2026-03-26 | D | 58 | CN002UD6982-2 | 002 | FW09 | CUTTING AND PREPARATION | FW | 4
75 | 2026-03-26 | D | 58 | CN002UD6982-2 | 002 | SW10 | CUTTING AND PREPARATION | SW | 4
76 | 2026-03-26 | D | 58 | CN002UD6982-2 | 002 | SW11 | CUTTING AND PREPARATION | SW | 4
77 | 2026-03-26 | D | 58 | CN007UD6955-2 | 002 | SW01 | CUTTING AND PREPARATION | SW | 4
78 | 2026-03-26 | D | 58 | CN007UD6955-2 | 002 | SW02 | CUTTING AND PREPARATION | SW | 4
79 | 2026-03-26 | D | 58 | CN007UD6955-2 | 002 | FW03 | CUTTING AND PREPARATION | FW | 4
80 | 2026-03-26 | D | 58 | CN007UD6955-2 | 002 | SW04 | CUTTING AND PREPARATION | SW | 4
81 | 2026-03-26 | D | 58 | CN007UD6955-2 | 002 | SW05 | CUTTING AND PREPARATION | SW | 4
82 | 2026-03-26 | D | 58 | CN007UD6955-2 | 002 | FW06 | CUTTING AND PREPARATION | FW | 4
83 | 2026-03-26 | D | 58 | CN007UD6955-2 | 002 | FW07 | CUTTING AND PREPARATION | FW | 4
84 | 2026-03-26 | D | 58 | CN002UD8667-1 | 001 | SW01 | CUTTING AND PREPARATION | SW | 4
85 | 2026-03-26 | D | 58 | CN002UD8667-1 | 001 | SW02 | CUTTING AND PREPARATION | SW | 4
86 | 2026-03-26 | D | 58 | CN002UD8667-1 | 001 | FW03 | CUTTING AND PREPARATION | FW | 4
87 | 2026-03-27 | D | 58 | CN002UD6955-1 | 001 | FW01 | CUTTING AND PREPARATION | FW | 4 | 8
88 | 2026-03-27 | D | 58 | CN002UD6955-1 | 001 | SW02 | CUTTING AND PREPARATION | SW | 4
89 | 2026-03-27 | D | 58 | CN002UD6955-1 | 001 | SW03 | CUTTING AND PREPARATION | SW | 4
90 | 2026-03-27 | D | 58 | CN002UD6955-1 | 001 | SW04 | CUTTING AND PREPARATION | SW | 4
91 | 2026-03-27 | D | 58 | CN002UD6955-1 | 001 | FW05 | CUTTING AND PREPARATION | FW | 4
92 | 2026-03-27 | D | 58 | CN002UD6955-1 | 001 | SW06 | CUTTING AND PREPARATION | SW | 4
93 | 2026-03-27 | D | 58 | CN002UD6955-1 | 001 | FW07 | CUTTING AND PREPARATION | FW | 4
94 | 2026-03-27 | D | 58 | CN002UD6955-1 | 001 | SW08 | CUTTING AND PREPARATION | SW | 4
95 | 2026-03-27 | D | 58 | CN002UD6955-1 | 001 | FW09 | CUTTING AND PREPARATION | FW | 4
96 | 2026-03-27 | D | 58 | CN002UD6976-3 | 003 | FW01 | CUTTING AND PREPARATION | FW | 4
97 | 2026-03-27 | D | 58 | CN002UD6976-3 | 003 | SW02 | CUTTING AND PREPARATION | SW | 4
98 | 2026-03-27 | D | 58 | CN002UD6976-3 | 003 | FW03 | CUTTING AND PREPARATION | FW | 4
99 | 2026-03-27 | D | 58 | CN002UD6976-4 | 004 | FW01 | CUTTING AND PREPARATION | FW | 4
100 | 2026-03-27 | D | 58 | CN002UD6976-4 | 004 | SW02 | CUTTING AND PREPARATION | SW | 4
101 | 2026-03-27 | D | 58 | CN002UD6976-4 | 004 | SW03 | CUTTING AND PREPARATION | SW | 4
102 | 2026-03-27 | D | 58 | CN002UD6976-4 | 004 | FW04 | CUTTING AND PREPARATION | FW | 4
103 | 2026-03-27 | D | 58 | CN002UD6976-4 | 004 | SW05 | CUTTING AND PREPARATION | SW | 4
104 | 2026-03-27 | D | 58 | CN002UD6976-4 | 004 | FW06 | CUTTING AND PREPARATION | FW | 4
105 | 2026-03-27 | D | 58 | CN002UD6976-5 | 005 | FW01 | CUTTING AND PREPARATION | FW | 4
106 | 2026-03-27 | D | 58 | CN002UD6976-5 | 005 | SW02 | CUTTING AND PREPARATION | SW | 4
107 | 2026-03-27 | D | 58 | CN002UD6976-5 | 005 | FW03 | CUTTING AND PREPARATION | FW | 4
108 | 2026-03-27 | D | 58 | CN002UD6976-6 | 006 | FW01 | CUTTING AND PREPARATION | FW | 4
109 | 2026-03-27 | D | 58 | CN002UD6976-6 | 006 | SW02 | CUTTING AND PREPARATION | SW | 4
110 | 2026-03-27 | D | 58 | CN002UD6976-6 | 006 | FW03 | CUTTING AND PREPARATION | FW | 4
111 | 2026-03-27 | D | 58 | CN002UD6976-6 | 006 | SW04 | CUTTING AND PREPARATION | SW | 4
112 | 2026-03-27 | D | 58 | CN002UD6976-6 | 006 | SW05 | CUTTING AND PREPARATION | SW | 4
113 | 2026-03-27 | D | 58 | CN002UD6976-6 | 006 | FW06 | CUTTING AND PREPARATION | FW | 4
114 | 2026-03-27 | D | 58 | CN002UD6976-6 | 006 | SW07 | CUTTING AND PREPARATION | SW | 4
115 | 2026-03-27 | D | 58 | CN002UD6976-6 | 006 | SW08 | CUTTING AND PREPARATION | SW | 4
116 | 2026-03-27 | D | 58 | CN002UD6977-1 | 001 | SW01 | CUTTING AND PREPARATION | SW | 4
117 | 2026-03-27 | D | 58 | CN002UD6977-1 | 001 | SW02 | CUTTING AND PREPARATION | SW | 4
118 | 2026-03-27 | D | 58 | CN002UD6977-1 | 001 | FW03 | CUTTING AND PREPARATION | FW | 4
119 | 2026-03-27 | D | 58 | CN002UD6977-1 | 001 | SW04 | CUTTING AND PREPARATION | SW | 4
120 | 2026-03-27 | D | 58 | CN002UD6977-1 | 001 | SW05 | CUTTING AND PREPARATION | SW | 4
121 | 2026-03-28 | DW | 58 | CN006UDW2148-1 | 001 | FW01 | CUTTING AND PREPARATION | FW | 3 | 8
122 | 2026-03-28 | DW | 58 | CN006UDW2148-1 | 001 | FW02 | CUTTING AND PREPARATION | FW | 3
123 | 2026-03-28 | DW | 58 | CN006UDW2148-1 | 001 | SW03 | CUTTING AND PREPARATION | SW | 3
124 | 2026-03-28 | DW | 58 | CN006UDW2148-1 | 001 | SW04 | CUTTING AND PREPARATION | SW | 3
125 | 2026-03-28 | DW | 58 | CN006UDW2148-1 | 001 | FW05 | CUTTING AND PREPARATION | FW | 3
126 | 2026-03-28 | DW | 58 | CN006UDW2148-1 | 001 | SW06 | CUTTING AND PREPARATION | SW | 3
127 | 2026-03-28 | DW | 58 | CN006UDW2148-1 | 001 | SW07 | CUTTING AND PREPARATION | SW | 3
128 | 2026-03-28 | DW | 58 | CN006UDW2148-1 | 001 | FW08 | CUTTING AND PREPARATION | FW | 3
129 | 2026-03-28 | DW | 58 | CN006UDW2148-1 | 001 | FW09 | CUTTING AND PREPARATION | FW | 3
130 | 2026-03-28 | DW | 58 | CN006UDW2148-1 | 001 | FW10 | CUTTING AND PREPARATION | FW | 3
131 | 2026-03-28 | DW | 58 | CN006UDW2148-1 | 001 | SW11 | CUTTING AND PREPARATION | SW | 3
132 | 2026-03-28 | DW | 58 | CN006UDW2148-1 | 001 | SW12 | CUTTING AND PREPARATION | SW | 3
133 | 2026-03-28 | DW | 58 | CN006UDW2148-1 | 001 | SW13 | CUTTING AND PREPARATION | SW | 3
134 | 2026-03-28 | DW | 58 | CN006UDW2148-2 | 002 | FW01 | CUTTING AND PREPARATION | FW | 3
135 | 2026-03-28 | DW | 58 | CN006UDW2148-2 | 002 | SW08 | CUTTING AND PREPARATION | SW | 3
136 | 2026-03-28 | DW | 58 | CN006UDW2148-2 | 002 | FW09 | CUTTING AND PREPARATION | FW | 3
137 | 2026-03-28 | DW | 58 | CN006UDW2148-2 | 002 | FW10 | CUTTING AND PREPARATION | FW | 3
138 | 2026-03-28 | DW | 58 | CN006UDW2148-2 | 002 | FW11 | CUTTING AND PREPARATION | FW | 3
139 | 2026-03-28 | DW | 58 | CN006UDW2148-2 | 002 | SW12 | CUTTING AND PREPARATION | SW | 3
140 | 2026-03-28 | DW | 58 | CN006UDW2148-2 | 002 | SW13 | CUTTING AND PREPARATION | SW | 3
141 | 2026-03-28 | DW | 58 | CN006UDW2148-2 | 002 | SW14 | CUTTING AND PREPARATION | SW | 3
142 | 2026-03-28 | DW | 58 | CN006UDW2148-2 | 002 | SW15 | CUTTING AND PREPARATION | SW | 3
143 | 2026-03-28 | DW | 58 | CN006UDW2148-2 | 002 | SW16 | CUTTING AND PREPARATION | SW | 3
144 | 2026-03-28 | DW | 58 | CN006UDW2148-2 | 002 | FW17 | CUTTING AND PREPARATION | FW | 3
145 | 2026-03-30 | FW | 58 | CN006UFW2365-1 | 001 | SW02 | ADHESIVE JOINT | SW | 6 | 8
146 | 2026-03-30 | FW | 58 | CN006UFW2365-1 | 001 | SW04 | ADHESIVE JOINT | SW | 6
147 | 2026-03-30 | FW | 58 | CN002UFW2442-1 | 001 | SW02 | ADHESIVE JOINT | SW | 6
148 | 2026-03-30 | FW | 58 | CN002UFW2442-2 | 002 | SW02 | ADHESIVE JOINT | SW | 6
149 | 2026-03-30 | FW | 58 | CN002UFW2447-1 | 001 | SW04 | ADHESIVE JOINT | SW | 6
150 | 2026-03-31 | FW | 58 | CN006UFW2525-1 | 001 | SW01 | ADHESIVE JOINT | SW | 4 | 7
151 | 2026-03-31 | FW | 58 | CN006UFW2525-1 | 001 | SW03 | ADHESIVE JOINT | SW | 4
152 | 2026-03-31 | FW | 58 | CN006UFW2525-1 | 001 | SW05 | ADHESIVE JOINT | SW | 4
153 | 2026-03-31 | FW | 58 | CN006UFW2525-1 | 001 | SW07 | ADHESIVE JOINT | SW | 4
154 | 2026-03-31 | FW | 58 | CN006UFW2525-1 | 001 | SW10 | ADHESIVE JOINT | SW | 4
155 | 2026-03-31 | FW | 58 | CN006UFW2525-1 | 001 | SW12 | ADHESIVE JOINT | SW | 4
156 | 2026-03-31 | FW | 58 | CN007UFW2453-1 | 001 | SW04 | ADHESIVE JOINT | SW | 6
157 | 2026-03-31 | FW | 58 | CN002UFW2442-2 | 002 | SW04 | ADHESIVE JOINT | SW | 6
158 | 2026-03-31 | D | 58 | CN002UD6955-1 | 001 | SW04 | ADHESIVE JOINT | SW | 4
159 | 2026-03-31 | D | 58 | CN002UD6955-1 | 001 | SW08 | ADHESIVE JOINT | SW | 4
160 | 2026-04-01 | D | 58 | CN002UD6955-1 | 001 | SW02 | ADHESIVE JOINT | SW | 4 | 8
161 | 2026-04-01 | D | 58 | CN002UD6955-3 | 003 | SW02 | ADHESIVE JOINT | SW | 4
162 | 2026-04-01 | D | 58 | CN002UD6955-4 | 004 | SW02 | ADHESIVE JOINT | SW | 4
163 | 2026-04-01 | FW | 58 | CN006UFW2525-1 | 001 | SW02 | ADHESIVE JOINT | SW | 4
164 | 2026-04-01 | FW | 58 | CN006UFW2525-1 | 001 | SW06 | ADHESIVE JOINT | SW | 4
165 | 2026-04-01 | FW | 58 | CN006UFW2525-1 | 001 | SW13 | ADHESIVE JOINT | SW | 4
166 | 2026-04-01 | FW | 58 | CN007UFW2453-1 | 001 | SW02 | ADHESIVE JOINT | SW | 6
167 | 2026-04-01 | FW | 58 | CN007UFW2453-1 | 001 | SW03 | ADHESIVE JOINT | SW | 6
168 | 2026-04-01 | FW | 58 | CN006UFW2365-1 | 001 | SW03 | ADHESIVE JOINT | SW | 6
169 | 2026-04-01 | FW | 58 | CN002UFW2442-2 | 002 | SW03 | ADHESIVE JOINT | SW | 6
170 | 2026-04-01 | FW | 58 | CN002UFW2447-1 | 001 | SW02 | ADHESIVE JOINT | SW | 6
171 | 2026-04-01 | FW | 58 | CN002UFW2447-1 | 001 | SW03 | ADHESIVE JOINT | SW | 6
172 | 2026-04-02 | D | 58 | CN002UD6955-4 | 004 | SW01 | ADHESIVE JOINT | SW | 4 | 7
173 | 2026-04-02 | D | 58 | CN002UD8667-1 | 001 | SW02 | ADHESIVE JOINT | SW | 4
174 | 2026-04-02 | FW | 58 | CN006UFW2525-1 | 001 | SW11 | ADHESIVE JOINT | SW | 4
175 | 2026-04-02 | D | 58 | CN002UD6976-3 | 003 | SW02 | ADHESIVE JOINT | SW | 4
176 | 2026-04-02 | D | 58 | CN002UD6976-4 | 004 | SW05 | ADHESIVE JOINT | SW | 4
177 | 2026-04-02 | D | 58 | CN002UD6976-4 | 004 | SW02 | ADHESIVE JOINT | SW | 4
178 | 2026-04-02 | D | 58 | CN002UD6976-5 | 005 | SW02 | ADHESIVE JOINT | SW | 4
179 | 2026-04-02 | D | 58 | CN002UD6976-6 | 006 | SW05 | ADHESIVE JOINT | SW | 4
180 | 2026-04-02 | D | 58 | CN002UD6976-6 | 006 | SW02 | ADHESIVE JOINT | SW | 4
181 | 2026-04-02 | D | 58 | CN002UD6977-1 | 001 | SW05 | ADHESIVE JOINT | SW | 4
182 | 2026-04-03 | D | 58 | CN002UD6982-2 | 002 | SW02 | ADHESIVE JOINT | SW | 4 | 8
183 | 2026-04-03 | D | 58 | CN002UD6982-2 | 002 | SW04 | ADHESIVE JOINT | SW | 4
184 | 2026-04-03 | D | 58 | CN002UD6982-2 | 002 | SW07 | ADHESIVE JOINT | SW | 4
185 | 2026-04-03 | D | 58 | CN002UD6982-2 | 002 | SW10 | ADHESIVE JOINT | SW | 4
186 | 2026-04-03 | D | 58 | CN002UD8667-1 | 001 | SW01 | ADHESIVE JOINT | SW | 4
187 | 2026-04-03 | D | 58 | CN007UD6955-1 | 001 | SW02 | ADHESIVE JOINT | SW | 4
188 | 2026-04-03 | D | 58 | CN007UD6955-1 | 001 | SW05 | ADHESIVE JOINT | SW | 4
189 | 2026-04-03 | D | 58 | CN002UD6976-4 | 004 | SW03 | ADHESIVE JOINT | SW | 4
190 | 2026-04-03 | D | 58 | CN002UD6977-1 | 001 | SW01 | ADHESIVE JOINT | SW | 4
191 | 2026-04-03 | D | 58 | CN002UD6977-1 | 001 | SW03 | ADHESIVE JOINT | SW | 4
192 | 2026-04-04 | D | 58 | CN002UD6982-2 | 002 | SW06 | ADHESIVE JOINT | SW | 4 | 8
193 | 2026-04-04 | D | 58 | CN002UD6982-2 | 002 | SW11 | ADHESIVE JOINT | SW | 4
194 | 2026-04-04 | D | 58 | CN007UD6955-2 | 002 | SW02 | ADHESIVE JOINT | SW | 4
195 | 2026-04-04 | D | 58 | CN007UD6955-2 | 002 | SW05 | ADHESIVE JOINT | SW | 4
196 | 2026-04-04 | D | 58 | CN007UD6955-1 | 001 | SW07 | ADHESIVE JOINT | SW | 4
197 | 2026-04-04 | D | 58 | CN007UD6955-1 | 001 | SW09 | ADHESIVE JOINT | SW | 4
198 | 2026-04-04 | D | 58 | CN002UD6976-6 | 006 | SW07 | ADHESIVE JOINT | SW | 4
199 | 2026-04-04 | D | 58 | CN002UD6977-1 | 001 | SW02 | ADHESIVE JOINT | SW | 4
200 | 2026-04-04 | D | 58 | CN006UD6674-1 | 001 | SW04 | ADHESIVE JOINT | SW | 4
201 | 2026-04-04 | D | 58 | CN006UD6674-1 | 001 | SW07 | ADHESIVE JOINT | SW | 4
202 | 2026-04-05 | REPAIR WORK FOR 8 " EXISTING LINE | [5 empty] | FW | 8 | 3
203 | 2026-04-06 | D | 58 | CN007UD6955-2 | 002 | SW01 | ADHESIVE JOINT | SW | 4 | 5
204 | 2026-04-06 | D | 58 | CN007UD6955-2 | 002 | SW04 | ADHESIVE JOINT | SW | 4
205 | 2026-04-06 | D | 58 | CN002UD6965-2 | 002 | SW05 | ADHESIVE JOINT | SW | 4
206 | 2026-04-06 | D | 58 | CN002UD6965-2 | 002 | SW06 | ADHESIVE JOINT | SW | 4
207 | 2026-04-06 | D | 58 | CN002UD6965-2 | 002 | SW09 | ADHESIVE JOINT | SW | 4
208 | 2026-04-06 | D | 58 | CN002UD6965-2 | 002 | SW10 | ADHESIVE JOINT | SW | 4
209 | 2026-04-06 | D | 58 | CN002UD6965-2 | 002 | SW14 | ADHESIVE JOINT | SW | 4
210 | 2026-04-06 | D | 58 | CN006UD6675-1 | 001 | SW06 | ADHESIVE JOINT | SW | 4
211 | 2026-04-06 | REPAIR WORK FOR 8 " EXISTING LINE | [5 empty] | FW | 8 | 3
212 | 2026-04-07 | D | 58 | CN002UD6976-6 | 006 | SW04 | ADHESIVE JOINT | SW | 4 | 7
213 | 2026-04-07 | D | 58 | CN002UD6965-2 | 002 | SW07 | ADHESIVE JOINT | SW | 4
214 | 2026-04-07 | D | 58 | CN002UD6965-2 | 002 | SW12 | ADHESIVE JOINT | SW | 4
215 | 2026-04-07 | D | 58 | CN006UD6675-1 | 001 | SW04 | ADHESIVE JOINT | SW | 4
216 | 2026-04-07 | FW | 58 | CN002UFW2444-1 | 001 | SW02 | ADHESIVE JOINT | SW | 8
217 | 2026-04-07 | FW | 58 | CN007UFW2457-1 | 001 | SW03 | ADHESIVE JOINT | SW | 8
218 | 2026-04-07 | FW | 58 | CN007UFW2458-1 | 001 | SW04 | ADHESIVE JOINT | SW | 8
219 | 2026-04-07 | D | 58 | CN002UD6955-6 | 006 | SW01 | ADHESIVE JOINT | SW | 4
220 | 2026-04-07 | D | 58 | CN002UD6955-6 | 006 | SW04 | ADHESIVE JOINT | SW | 4
221 | 2026-04-07 | D | 58 | CN002UD6955-6 | 006 | SW06 | ADHESIVE JOINT | SW | 4
222 | 2026-04-09 | FW | 58 | CN002UFW2444-1 | 001 | SW03 | ADHESIVE JOINT | SW | 8 | 8
223 | 2026-04-09 | FW | 58 | CN002UFW2444-1 | 001 | SW04 | ADHESIVE JOINT | SW | 8
224 | 2026-04-09 | FW | 58 | CN007UFW2457-1 | 001 | SW02 | ADHESIVE JOINT | SW | 8
225 | 2026-04-09 | FW | 58 | CN002UFW2457-1 | 001 | SW03 | ADHESIVE JOINT | SW | 8
226 | 2026-04-09 | FW | 58 | CN006UFW2366-1 | 001 | SW01 | ADHESIVE JOINT | SW | 8
227 | 2026-04-09 | FW | 58 | CN006UFW2366-1 | 001 | SW02 | ADHESIVE JOINT | SW | 8
228 | 2026-04-09 | FW | 58 | CN006UFW2366-1 | 001 | SW03 | ADHESIVE JOINT | SW | 8
229 | 2026-04-09 | FW | 58 | CN006UFW2366-1 | 001 | SW05 | ADHESIVE JOINT | SW | 8
230 | 2026-04-09 | FW | 58 | CN006UFW2361-1 | 001 | SW07 | ADHESIVE JOINT | SW | 8
231 | 2026-04-09 | FW | 58 | CN006UFW2361-1 | 001 | SW13 | ADHESIVE JOINT | SW | 8
232 | 2026-04-10 | FW | 58 | CN002UFW2447-1 | 001 | SW02 | LAMINATION | SW | 6 | 8
233 | 2026-04-10 | FW | 58 | CN002UFW2447-1 | 001 | SW03 | LAMINATION | SW | 6
234 | 2026-04-10 | FW | 58 | CN007UFW2458-1 | 001 | SW06 | ADHESIVE JOINT | SW | 8
235 | 2026-04-10 | FW | 58 | CN006UFW2366-2 | 002 | SW14 | ADHESIVE JOINT | SW | 8
236 | 2026-04-10 | FW | 58 | CN006UFW2366-2 | 002 | SW15 | ADHESIVE JOINT | SW | 8
237 | 2026-04-10 | FW | 58 | CN006UFW2366-3 | 003 | SW06 | ADHESIVE JOINT | SW | 8
238 | 2026-04-10 | FW | 58 | CN006UFW2361-1 | 001 | SW09 | ADHESIVE JOINT | SW | 8
239 | 2026-04-11 | FW | 58 | CN007UFW2453-1 | 001 | SW02 | LAMINATION | SW | 6 | 6
240 | 2026-04-11 | FW | 58 | CN007UFW2453-1 | 001 | SW03 | LAMINATION | SW | 6
241 | 2026-04-11 | FW | 58 | CN007UFW2453-1 | 001 | SW04 | LAMINATION | SW | 6
242 | 2026-04-11 | FW | 58 | CN002UFW2442-1 | 001 | SW02 | LAMINATION | SW | 6
243 | 2026-04-11 | FW | 58 | CN002UFW2442-2 | 002 | SW02 | LAMINATION | SW | 6
244 | 2026-04-11 | FW | 58 | CN002UFW2442-2 | 002 | SW03 | LAMINATION | SW | 6
245 | 2026-04-11 | FW | 58 | CN002UFW2442-2 | 002 | SW04 | LAMINATION | SW | 6
246 | 2026-04-11 | FW | 58 | CN002UFW2447-1 | 001 | SW04 | LAMINATION | SW | 6
247 | 2026-04-13 | D | 58 | CN006UD6675-1 | 001 | SW05 | ADHESIVE JOINT | SW | 4 | 8
248 | 2026-04-13 | D | 58 | CN002UD6955-6 | 006 | SW03 | ADHESIVE JOINT | SW | 4
249 | 2026-04-13 | FW | 58 | CN006UFW2366-4 | 004 | SW03 | ADHESIVE JOINT | SW | 8
250 | 2026-04-13 | FW | 58 | CN006UFW2525-1 | 001 | SW01 | LAMINATION | SW | 4
251 | 2026-04-13 | FW | 58 | CN006UFW2525-1 | 001 | SW02 | LAMINATION | SW | 4
252 | 2026-04-13 | FW | 58 | CN006UFW2525-1 | 001 | SW03 | LAMINATION | SW | 4
253 | 2026-04-13 | FW | 58 | CN006UFW2525-1 | 001 | SW05 | LAMINATION | SW | 4
254 | 2026-04-13 | FW | 58 | CN006UFW2525-1 | 001 | SW06 | LAMINATION | SW | 4
255 | 2026-04-13 | FW | 58 | CN006UFW2525-1 | 001 | SW07 | LAMINATION | SW | 4
256 | 2026-04-13 | FW | 58 | CN006UFW2525-1 | 001 | SW10 | LAMINATION | SW | 4
257 | 2026-04-13 | FW | 58 | CN006UFW2525-1 | 001 | SW11 | LAMINATION | SW | 4
258 | 2026-04-13 | FW | 58 | CN006UFW2525-1 | 001 | SW12 | LAMINATION | SW | 4
259 | 2026-04-13 | FW | 58 | CN006UFW2525-1 | 001 | SW13 | LAMINATION | SW | 4
260 | 2026-04-14 | D | 58 | CN002UD6955-4 | 004 | SW01 | LAMINATION | SW | 4 | 8
261 | 2026-04-14 | D | 58 | CN002UD6955-4 | 004 | SW02 | LAMINATION | SW | 4
262 | 2026-04-14 | D | 58 | CN002UD6982-2 | 002 | SW02 | LAMINATION | SW | 4
263 | 2026-04-14 | D | 58 | CN002UD6982-2 | 002 | SW04 | LAMINATION | SW | 4
264 | 2026-04-14 | D | 58 | CN002UD6982-2 | 002 | SW06 | LAMINATION | SW | 4
265 | 2026-04-14 | D | 58 | CN002UD6982-2 | 002 | SW07 | LAMINATION | SW | 4
266 | 2026-04-14 | D | 58 | CN002UD6982-2 | 002 | SW10 | LAMINATION | SW | 4
267 | 2026-04-14 | D | 58 | CN002UD6982-2 | 002 | SW11 | LAMINATION | SW | 4
268 | 2026-04-14 | D | 58 | CN002UD6976-3 | 003 | SW01 | LAMINATION | SW | 4
269 | 2026-04-14 | D | 58 | CN002UD6976-4 | 004 | SW02 | LAMINATION | SW | 4
270 | 2026-04-14 | D | 58 | CN002UD6976-4 | 004 | SW03 | LAMINATION | SW | 4
271 | 2026-04-14 | D | 58 | CN002UD6977-1 | 001 | SW05 | LAMINATION | SW | 4
272 | 2026-04-14 | D | 58 | CN002UD6977-1 | 001 | SW02 | LAMINATION | SW | 4
273 | 2026-04-14 | D | 58 | CN002UD6977-1 | 001 | SW01 | LAMINATION | SW | 4
274 | 2026-04-14 | D | 58 | CN002UD6977-1 | 001 | SW03 | LAMINATION | SW | 4
275 | 2026-04-15 | D | 58 | CN002UD6955-3 | 003 | SW02 | LAMINATION | SW | 4 | 7
276 | 2026-04-15 | D | 58 | CN007UD6955-2 | 002 | SW01 | LAMINATION | SW | 4
277 | 2026-04-15 | D | 58 | CN007UD6955-2 | 002 | SW02 | LAMINATION | SW | 4
278 | 2026-04-15 | D | 58 | CN007UD6955-2 | 002 | SW04 | LAMINATION | SW | 4
279 | 2026-04-15 | D | 58 | CN007UD6955-2 | 002 | SW05 | LAMINATION | SW | 4
280 | 2026-04-15 | D | 58 | CN002UD6976-4 | 004 | SW05 | LAMINATION | SW | 4
281 | 2026-04-15 | D | 58 | CN002UD6976-5 | 005 | SW02 | LAMINATION | SW | 4
282 | 2026-04-15 | D | 58 | CN002UD6976-6 | 006 | SW05 | LAMINATION | SW | 4
283 | 2026-04-15 | D | 58 | CN002UD6976-6 | 006 | SW07 | LAMINATION | SW | 4
284 | 2026-04-15 | D | 58 | CN002UD6976-6 | 006 | SW04 | LAMINATION | SW | 4
285 | 2026-04-16 | D | 58 | CN007UD6955-1 | 001 | SW05 | LAMINATION | SW | 4 | 7
286 | 2026-04-16 | D | 58 | CN002UD6955-1 | 001 | SW02 | LAMINATION | SW | 4
287 | 2026-04-16 | D | 58 | CN002UD6955-1 | 001 | SW04 | LAMINATION | SW | 4
288 | 2026-04-16 | D | 58 | CN002UD6955-1 | 001 | SW08 | LAMINATION | SW | 4
289 | 2026-04-16 | D | 58 | CN002UD6976-6 | 006 | SW02 | LAMINATION | SW | 4
290 | 2026-04-16 | D | 58 | CN002UD6965-2 | 002 | SW05 | LAMINATION | SW | 4
291 | 2026-04-16 | D | 58 | CN002UD6965-2 | 002 | SW06 | LAMINATION | SW | 4
292 | 2026-04-16 | D | 58 | CN002UD6965-2 | 002 | SW07 | LAMINATION | SW | 4
293 | 2026-04-16 | D | 58 | CN002UD6965-2 | 002 | SW09 | LAMINATION | SW | 4
294 | 2026-04-16 | D | 58 | CN002UD6965-2 | 002 | SW10 | LAMINATION | SW | 4
295 | 2026-04-16 | D | 58 | CN002UD6965-2 | 002 | SW13 | ADHESIVE JOINT | SW | 4
296 | 2026-04-17 | D | 58 | CN007UD6955-1 | 001 | SW10 | ADHESIVE JOINT | SW | 4 | 8 | Due to the absence of ADPF supervisor, no lamination was done
297 | 2026-04-17 | D | 58 | CN006UD6674-1 | 001 | SW01 | ADHESIVE JOINT | SW | 4
298 | 2026-04-17 | D | 58 | CN006UD6674-1 | 001 | SW05 | ADHESIVE JOINT | SW | 4 |  | Preparatory works for 82 joints done along with 28" adhesive joints
299 | 2026-04-17 | FW | 58 | CN007UFW2458-1 | 001 | SW05 | ADHESIVE JOINT | SW | 8
300 | 2026-04-17 | FW | 58 | CN007UFW2458-1 | 001 | SW06 | ADHESIVE JOINT | SW | 8
301 | 2026-04-18 | D | 58 | CN006UD6674-1 | 001 | SW02 | ADHESIVE JOINT | SW | 4 | 7 | Due to the absence of ADPF supervisor, no lamination was done
302 | 2026-04-18 | D | 58 | CN001UD8648-1 | 001 | SW01 | ADHESIVE JOINT | SW | 4
303 | 2026-04-18 | D | 58 | CN001UD8648-1 | 001 | SW02 | ADHESIVE JOINT | SW | 4
304 | 2026-04-18 | D | 58 | CN006UD6675-10 | 010 | SW01 | ADHESIVE JOINT | SW | 4
305 | 2026-04-18 | D | 58 | CN006UD6675-10 | 010 | SW02 | ADHESIVE JOINT | SW | 4
306 | 2026-04-18 | D | 58 | CN006UD6675-10 | 010 | SW04 | ADHESIVE JOINT | SW | 4
307 | 2026-04-18 | D | 58 | CN006UD6675-10 | 010 | SW06 | ADHESIVE JOINT | SW | 4
308 | 2026-04-18 | D | 58 | CN006UD6675-11 | 011 | SW08 | ADHESIVE JOINT | SW | 4
309 | 2026-04-18 | D | 58 | CN006UD6675-13 | 013 | SW05 | ADHESIVE JOINT | SW | 4
310 | 2026-04-18 | D | 58 | CN006UD6675-13 | 013 | SW12 | ADHESIVE JOINT | SW | 4
311 | 2026-04-18 | D | 58 | CN006UD6675-13 | 013 | SW15 | ADHESIVE JOINT | SW | 4
312 | 2026-04-18 | D | 58 | CN006UD6675-14 | 014 | SW03 | ADHESIVE JOINT | SW | 4
313 | 2026-04-18 | D | 58 | CN006UD6675-14 | 014 | SW05 | ADHESIVE JOINT | SW | 4
314 | 2026-04-18 | D | 58 | CN006UD6675-14 | 014 | SW09 | ADHESIVE JOINT | SW | 4
315 | 2026-04-18 | D | 58 | CN006UD6675-2 | 002 | SW10 | ADHESIVE JOINT | SW | 4
316 | 2026-04-20 | D | 58 | CN006UD6675-10 | 010 | SW07 | ADHESIVE JOINT | SW | 4 | 6
317 | 2026-04-20 | D | 58 | CN006UD6675-11 | 011 | SW10 | ADHESIVE JOINT | SW | 4
318 | 2026-04-20 | D | 58 | CN006UD6675-11 | 011 | SW16 | ADHESIVE JOINT | SW | 4
319 | 2026-04-20 | D | 58 | CN006UD6675-12 | 012 | SW03 | ADHESIVE JOINT | SW | 4
320 | 2026-04-20 | D | 58 | CN006UD6675-13 | 013 | SW03 | ADHESIVE JOINT | SW | 4
321 | 2026-04-20 | D | 58 | CN006UD6675-13 | 013 | SW10 | ADHESIVE JOINT | SW | 4
322 | 2026-04-20 | D | 58 | CN006UD6675-14 | 014 | SW07 | ADHESIVE JOINT | SW | 4
323 | 2026-04-20 | D | 58 | CN002UFW2444-1 | 001 | SW02 | LAMINATION | SW | 8
324 | 2026-04-20 | D | 58 | CN002UFW2444-1 | 001 | SW03 | LAMINATION | SW | 8
325 | 2026-04-20 | D | 58 | CN007UFW2457-1 | 001 | SW02 | LAMINATION | SW | 8
326 | 2026-04-20 | D | 58 | CN007UFW2457-1 | 001 | SW03 | LAMINATION | SW | 8
327 | 2026-04-21 | D | 58 | CN002UD8667-1 | 001 | SW01 | LAMINATION | SW | 4 | 6
328 | 2026-04-21 | D | 58 | CN002UD8667-1 | 001 | SW02 | LAMINATION | SW | 4
329 | 2026-04-21 | D | 58 | CN007UD6955-1 | 001 | SW02 | LAMINATION | SW | 4
330 | 2026-04-21 | D | 58 | CN002UD6965-2 | 002 | SW12 | LAMINATION | SW | 4
331 | 2026-04-21 | D | 58 | CN002UD6965-2 | 002 | SW13 | LAMINATION | SW | 4
332 | 2026-04-21 | D | 58 | CN002UD6965-2 | 002 | SW14 | LAMINATION | SW | 4
333 | 2026-04-21 | D | 58 | CN006UD6674-1 | 001 | SW07 | LAMINATION | SW | 4
334 | 2026-04-21 | FW | 58 | CN002UFW2444-1 | 001 | SW01 | LAMINATION | SW | 8
335 | 2026-04-21 | D | 58 | CN002UD6955-6 | 006 | SW03 | LAMINATION | SW | 4
336 | 2026-04-21 | D | 58 | CN002UD6955-6 | 006 | SW04 | LAMINATION | SW | 4
337 | 2026-04-21 | D | 58 | CN006UD6675-14 | 014 | SW05 | LAMINATION | SW | 4
338 | 2026-04-22 | D | 58 | CN006UD6674-1 | 001 | SW01 | LAMINATION | SW | 4 | 4
339 | 2026-04-22 | D | 58 | CN006UD6674-1 | 001 | SW02 | LAMINATION | SW | 4
340 | 2026-04-22 | D | 58 | CN006UD6675-1 | 001 | SW08 | LAMINATION | SW | 4
341 | 2026-04-22 | D | 58 | CN002UD6955-6 | 006 | SW01 | LAMINATION | SW | 4
342 | 2026-04-22 | D | 58 | CN002UD6955-6 | 006 | SW02 | LAMINATION | SW | 4
343 | 2026-04-22 | D | 58 | CN006UD6675-10 | 010 | SW04 | LAMINATION | SW | 4
344 | 2026-04-22 | D | 58 | CN006UD6675-13 | 013 | SW05 | LAMINATION | SW | 4
345 | 2026-04-22 | D | 58 | CN006UD6675-13 | 013 | SW12 | LAMINATION | SW | 4
346 | 2026-04-22 | D | 58 | CN006UD6675-14 | 014 | SW09 | LAMINATION | SW | 4
347 | 2026-04-23 | D | 58 | CN006UD6675-11 | 011 | SW12 | ADHESIVE JOINT | SW | 4 | 6
348 | 2026-04-23 | D | 58 | CN006UD6675-11 | 011 | SW15 | ADHESIVE JOINT | SW | 4
349 | 2026-04-23 | D | 58 | CN006UD6675-3 | 003 | SW05 | ADHESIVE JOINT | SW | 4
350 | 2026-04-23 | D | 58 | CN006UD6675-3 | 003 | SW07 | ADHESIVE JOINT | SW | 4
351 | 2026-04-23 | D | 58 | CN006UD6675-4 | 004 | SW10 | ADHESIVE JOINT | SW | 4
352 | 2026-04-23 | D | 58 | CN006UD6705-1 | 001 | SW08 | ADHESIVE JOINT | SW | 4
353 | 2026-04-23 | D | 58 | CN001UD8648-1 | 001 | SW01 | LAMINATION | SW | 4
354 | 2026-04-23 | D | 58 | CN001UD8648-1 | 001 | SW02 | LAMINATION | SW | 4
355 | 2026-04-23 | D | 58 | CN006UD6675-13 | 013 | SW15 | LAMINATION | SW | 4
356 | 2026-04-23 | D | 58 | CN006UD6675-14 | 014 | SW03 | LAMINATION | SW | 4
357 | 2026-04-23 | D | 58 | CN006UD6675-14 | 014 | SW07 | LAMINATION | SW | 4
358 | 2026-04-23 | D | 58 | CN007UD6955-1 | 001 | SW07 | LAMINATION | SW | 4
359 | 2026-04-24 | D | 58 | CN006UD6675-1 | 001 | SW03 | ADHESIVE JOINT | SW | 4 | 6
360 | 2026-04-24 | D | 58 | CN006UD6675-11 | 011 | SW14 | ADHESIVE JOINT | SW | 4
361 | 2026-04-24 | D | 58 | CN006UD6675-2 | 002 | SW04 | ADHESIVE JOINT | SW | 4
362 | 2026-04-24 | D | 58 | CN006UD6675-2 | 002 | SW05 | ADHESIVE JOINT | SW | 4
363 | 2026-04-24 | D | 58 | CN006UD6675-2 | 002 | SW15 | ADHESIVE JOINT | SW | 4
364 | 2026-04-24 | D | 58 | CN006UD6675-4 | 004 | SW04 | ADHESIVE JOINT | SW | 4
365 | 2026-04-24 | D | 58 | CN006UD6675-4 | 004 | SW08 | ADHESIVE JOINT | SW | 4
366 | 2026-04-24 | D | 58 | CN006UD6675-5 | 005 | SW02 | ADHESIVE JOINT | SW | 4
367 | 2026-04-24 | D | 58 | CN006UD6675-5 | 005 | SW04 | ADHESIVE JOINT | SW | 4
368 | 2026-04-24 | D | 58 | CN006UD6675-5 | 005 | SW06 | ADHESIVE JOINT | SW | 4
369 | 2026-04-24 | D | 58 | CN006UD6675-6 | 006 | SW03 | ADHESIVE JOINT | SW | 4
370 | 2026-04-24 | D | 58 | CN006UD6675-7 | 007 | SW14 | ADHESIVE JOINT | SW | 4
371 | 2026-04-24 | D | 58 | CN006UD6675-8 | 008 | SW04 | ADHESIVE JOINT | SW | 4
372 | 2026-04-24 | D | 58 | CN006UD6675-8 | 008 | SW05 | ADHESIVE JOINT | SW | 4
373 | 2026-04-24 | D | 58 | CN002UD6955-6 | 006 | SW06 | LAMINATION | SW | 4
374 | 2026-04-24 | D | 58 | CN006UD6675-11 | 011 | SW15 | LAMINATION | SW | 4
375 | 2026-04-24 | D | 58 | CN006UD6675-11 | 011 | SW16 | LAMINATION | SW | 4
376 | 2026-04-24 | D | 58 | CN006UD6675-3 | 003 | SW05 | LAMINATION | SW | 4
377 | 2026-04-24 | D | 58 | CN006UD6675-3 | 003 | SW07 | LAMINATION | SW | 4
378 | 2026-04-24 | D | 58 | CN006UD6705-1 | 001 | SW08 | LAMINATION | SW | 4
379 | 2026-04-25 | D | 58 | CN001UD8648-1 | 001 | SW04 | ADHESIVE JOINT | SW | 4 | 6
380 | 2026-04-25 | D | 58 | CN001UD8648-1 | 001 | SW06 | ADHESIVE JOINT | SW | 4
381 | 2026-04-25 | D | 58 | CN006UD6675-11 | 011 | SW02 | ADHESIVE JOINT | SW | 4
382 | 2026-04-25 | D | 58 | CN006UD6675-11 | 011 | SW04 | ADHESIVE JOINT | SW | 4
383 | 2026-04-25 | D | 58 | CN006UD6675-3 | 003 | SW03 | ADHESIVE JOINT | SW | 4
384 | 2026-04-25 | D | 58 | CN006UD6675-4 | 004 | SW01 | ADHESIVE JOINT | SW | 4
385 | 2026-04-25 | D | 58 | CN006UD6675-4 | 004 | SW13 | ADHESIVE JOINT | SW | 4
386 | 2026-04-25 | D | 58 | CN006UD6675-4 | 004 | SW15 | ADHESIVE JOINT | SW | 4
387 | 2026-04-25 | D | 58 | CN006UD6675-5 | 005 | SW01 | ADHESIVE JOINT | SW | 4
388 | 2026-04-25 | D | 58 | CN006UD6675-7 | 007 | SW07 | ADHESIVE JOINT | SW | 4
389 | 2026-04-25 | D | 58 | CN006UD6675-11 | 011 | SW14 | LAMINATION | SW | 4
390 | 2026-04-25 | D | 58 | CN006UD6675-12 | 012 | SW03 | LAMINATION | SW | 4
391 | 2026-04-25 | D | 58 | CN006UD6675-6 | 006 | SW03 | LAMINATION | SW | 4
392 | 2026-04-25 | D | 58 | CN006UD6675-8 | 008 | SW04 | LAMINATION | SW | 4
393 | 2026-04-25 | D | 58 | CN006UD6675-8 | 008 | SW05 | LAMINATION | SW | 4
394 | 2026-04-27 | D | 58 | CN001UD8648-1 | 001 | SW04 | LAMINATION | SW | 4 | 6
395 | 2026-04-27 | D | 58 | CN006UD6675-10 | 010 | SW01 | LAMINATION | SW | 4
396 | 2026-04-27 | D | 58 | CN006UD6675-10 | 010 | SW02 | LAMINATION | SW | 4
397 | 2026-04-27 | D | 58 | CN006UD6675-10 | 010 | SW06 | LAMINATION | SW | 4
398 | 2026-04-27 | D | 58 | CN006UD6675-10 | 010 | SW07 | LAMINATION | SW | 4
399 | 2026-04-27 | D | 58 | CN006UD6675-2 | 002 | SW10 | LAMINATION | SW | 4
400 | 2026-04-27 | D | 58 | CN006UD6675-2 | 002 | SW15 | LAMINATION | SW | 4
401 | 2026-04-27 | D | 58 | CN006UD6675-4 | 004 | SW04 | LAMINATION | SW | 4
402 | 2026-04-27 | D | 58 | CN006UD6675-4 | 004 | SW08 | LAMINATION | SW | 4
403 | 2026-04-27 | D | 58 | CN006UD6675-5 | 005 | SW01 | LAMINATION | SW | 4
404 | 2026-04-27 | D | 58 | CN006UD6675-5 | 005 | SW02 | LAMINATION | SW | 4
405 | 2026-04-27 | D | 58 | CN006UD6675-5 | 005 | SW06 | LAMINATION | SW | 4
406 | 2026-04-27 | D | 58 | CN006UD6675-13 | 013 | SW07 | ADHESIVE JOINT | SW | 4
407 | 2026-04-27 | D | 58 | CN006UD6675-2 | 002 | SW08 | ADHESIVE JOINT | SW | 4
408 | 2026-04-27 | D | 58 | CN006UD6675-2 | 002 | SW11 | ADHESIVE JOINT | SW | 4
409 | 2026-04-27 | D | 58 | CN006UD6675-3 | 003 | SW09 | ADHESIVE JOINT | SW | 4
410 | 2026-04-27 | D | 58 | CN006UD6675-3 | 003 | SW13 | ADHESIVE JOINT | SW | 4
411 | 2026-04-27 | D | 58 | CN006UD6675-7 | 007 | SW01 | ADHESIVE JOINT | SW | 4
412 | 2026-04-27 | D | 58 | CN006UD6675-7 | 007 | SW10 | ADHESIVE JOINT | SW | 4
413 | 2026-04-28 | D | 58 | CN006UD6675-6 | 006 | SW02 | ADHESIVE JOINT | SW | 4 | 7
414 | 2026-04-28 | D | 58 | CN006UD6705-1 | 001 | SW06 | ADHESIVE JOINT | SW | 4
415 | 2026-04-28 | D | 58 | CN006UD6705-1 | 001 | SW10 | ADHESIVE JOINT | SW | 4
416 | 2026-04-28 | D | 58 | CN006UD6675-8 | 008 | SW10 | ADHESIVE JOINT | SW | 4
417 | 2026-04-28 | D | 58 | CN006UD6707-1 | 001 | SW06 | ADHESIVE JOINT | SW | 4
418 | 2026-04-28 | D | 58 | CN006UD6743-1 | 001 | SW10 | ADHESIVE JOINT | SW | 4
419 | 2026-04-28 | D | 58 | CN007UD6955-1 | 001 | SW09 | LAMINATION | SW | 4
420 | 2026-04-28 | D | 58 | CN006UD6674-1 | 001 | SW04 | LAMINATION | SW | 4
421 | 2026-04-28 | D | 58 | CN006UD6674-1 | 001 | SW05 | LAMINATION | SW | 4
422 | 2026-04-28 | D | 58 | CN006UD6675-11 | 011 | SW02 | LAMINATION | SW | 4
423 | 2026-04-28 | D | 58 | CN006UD6675-11 | 011 | SW04 | LAMINATION | SW | 4
424 | 2026-04-28 | D | 58 | CN006UD6675-2 | 002 | SW04 | LAMINATION | SW | 4
425 | 2026-04-28 | D | 58 | CN006UD6675-2 | 002 | SW05 | LAMINATION | SW | 4
426 | 2026-04-28 | D | 58 | CN006UD6675-3 | 003 | SW03 | LAMINATION | SW | 4
427 | 2026-04-28 | D | 58 | CN006UD6675-4 | 004 | SW15 | LAMINATION | SW | 4
428 | 2026-04-28 | D | 58 | CN006UD6675-7 | 007 | SW07 | LAMINATION | SW | 4
429 | 2026-04-29 | D | 58 | CN001UD8648-1 | 001 | SW04 | ADHESIVE JOINT | SW | 4 | 7
430 | 2026-04-29 | D | 58 | CN006UD6675-10 | 010 | SW01 | ADHESIVE JOINT | SW | 4
431 | 2026-04-29 | D | 58 | CN006UD6675-10 | 010 | SW02 | ADHESIVE JOINT | SW | 4
432 | 2026-04-29 | D | 58 | CN006UD6675-10 | 010 | SW06 | ADHESIVE JOINT | SW | 4
433 | 2026-04-29 | D | 58 | CN006UD6675-10 | 010 | SW07 | ADHESIVE JOINT | SW | 4
434 | 2026-04-29 | D | 58 | CN006UD6675-2 | 002 | SW10 | ADHESIVE JOINT | SW | 4
435 | 2026-04-29 | D | 58 | CN006UD6675-2 | 002 | SW15 | ADHESIVE JOINT | SW | 4
436 | 2026-04-29 | D | 58 | CN006UD6675-4 | 004 | SW04 | ADHESIVE JOINT | SW | 4
437 | 2026-04-29 | D | 58 | CN006UD6675-4 | 004 | SW08 | ADHESIVE JOINT | SW | 4
438 | 2026-04-29 | D | 58 | CN006UD6675-5 | 005 | SW01 | ADHESIVE JOINT | SW | 4
439 | 2026-04-29 | D | 58 | CN006UD6675-5 | 005 | SW02 | ADHESIVE JOINT | SW | 4
440 | 2026-04-29 | D | 58 | CN006UD6675-5 | 005 | SW06 | ADHESIVE JOINT | SW | 4
441 | 2026-04-29 | D | 58 | CN001UD8648-1 | 001 | SW06 | LAMINATION | SW | 4
442 | 2026-04-29 | D | 58 | CN006UD6675-11 | 011 | SW08 | LAMINATION | SW | 4
443 | 2026-04-29 | D | 58 | CN006UD6675-13 | 013 | SW03 | LAMINATION | SW | 4
444 | 2026-04-29 | D | 58 | CN006UD6675-3 | 003 | SW13 | LAMINATION | SW | 4
445 | 2026-04-29 | D | 58 | CN006UD6675-5 | 005 | SW04 | LAMINATION | SW | 4
446 | 2026-04-29 | D | 58 | CN006UD6705-1 | 001 | SW06 | LAMINATION | SW | 4
447 | 2026-04-29 | D | 58 | CN006UD6705-1 | 001 | SW10 | LAMINATION | SW | 4
448 | 2026-04-29 | D | 58 | CN006UD6675-8 | 008 | SW10 | LAMINATION | SW | 4
449 | 2026-04-29 | D | 58 | CN006UD6707-1 | 001 | SW06 | LAMINATION | SW | 4
450 | 2026-04-29 | D | 58 | CN006UD6743-1 | 001 | SW10 | LAMINATION | SW | 4
451 | 2026-04-30 | D | 58 | CN006UD6675-13 | 013 | SW02 | ADHESIVE JOINT | SW | 4 | 7
452 | 2026-04-30 | D | 58 | CN006UD6675-14 | 014 | SW02 | ADHESIVE JOINT | SW | 4
453 | 2026-04-30 | D | 58 | CN006UD6675-2 | 002 | SW02 | ADHESIVE JOINT | SW | 4
454 | 2026-04-30 | D | 58 | CN006UD6705-1 | 001 | SW03 | ADHESIVE JOINT | SW | 4
455 | 2026-04-30 | D | 58 | CN006UD6705-1 | 001 | SW12 | ADHESIVE JOINT | SW | 4
456 | 2026-04-30 | D | 58 | CN006UD6675-7 | 007 | SW11 | ADHESIVE JOINT | SW | 4
457 | 2026-04-30 | D | 58 | CN006UD6675-8 | 008 | SW01 | ADHESIVE JOINT | SW | 4
458 | 2026-04-30 | D | 58 | CN006UD6695-1 | 001 | SW01 | ADHESIVE JOINT | SW | 4
459 | 2026-04-30 | D | 58 | CN006UD6675-11 | 011 | SW01 | LAMINATION | SW | 4
460 | 2026-04-30 | D | 58 | CN006UD6675-13 | 013 | SW07 | LAMINATION | SW | 4
461 | 2026-04-30 | D | 58 | CN006UD6675-13 | 013 | SW08 | LAMINATION | SW | 4
462 | 2026-04-30 | D | 58 | CN006UD6675-4 | 004 | SW01 | LAMINATION | SW | 4
463 | 2026-04-30 | D | 58 | CN006UD6675-4 | 004 | SW02 | LAMINATION | SW | 4
464 | 2026-04-30 | D | 58 | CN006UD6675-7 | 007 | SW01 | LAMINATION | SW | 4
465 | 2026-04-30 | D | 58 | CN006UD6675-7 | 007 | SW02 | LAMINATION | SW | 4
466 | 2026-04-30 | D | 58 | CN006UD6675-7 | 007 | SW14 | LAMINATION | SW | 4
467 | 2026-04-30 | D | 58 | CN006UD6743-4 | 004 | SW04 | LAMINATION | SW | 4
468 | 2026-04-30 | D | 58 | CN006UD6747-2 | 002 | SW05 | LAMINATION | SW | 4
469 | 2026-05-01 | D | 58 | CN006UD6705-1 | 001 | SW01 | ADHESIVE JOINT | SW | 4 | 6
470 | 2026-05-01 | D | 58 | CN006UD6705-1 | 001 | SW02 | ADHESIVE JOINT | SW | 4
471 | 2026-05-01 | D | 58 | CN006UD6675-7 | 007 | SW12 | ADHESIVE JOINT | SW | 4
472 | 2026-05-01 | D | 58 | CN006UD6695-1 | 001 | SW02 | ADHESIVE JOINT | SW | 4
473 | 2026-05-01 | D | 58 | CN006UD6701-1 | 001 | SW04 | ADHESIVE JOINT | SW | 4
474 | 2026-05-01 | D | 58 | CN006UD6743-2 | 002 | SW01 | ADHESIVE JOINT | SW | 4
475 | 2026-05-01 | D | 58 | CN006UD6743-2 | 002 | SW03 | ADHESIVE JOINT | SW | 4
476 | 2026-05-01 | D | 58 | CN006UD6743-3 | 003 | SW14 | ADHESIVE JOINT | SW | 4
477 | 2026-05-01 | D | 58 | CN006UD6743-4 | 004 | SW07 | ADHESIVE JOINT | SW | 4
478 | 2026-05-01 | D | 58 | CN006UD8649-1 | 001 | SW01 | ADHESIVE JOINT | SW | 4
479 | 2026-05-01 | D | 58 | CN006UD8650-1 | 001 | SW01 | ADHESIVE JOINT | SW | 4
480 | 2026-05-01 | D | 58 | CN006UD6675-13 | 013 | SW14 | LAMINATION | SW | 4
481 | 2026-05-01 | D | 58 | CN006UD6675-2 | 002 | SW01 | LAMINATION | SW | 4
482 | 2026-05-01 | D | 58 | CN006UD6675-2 | 002 | SW02 | LAMINATION | SW | 4
483 | 2026-05-01 | D | 58 | CN006UD6705-1 | 001 | SW03 | LAMINATION | SW | 4
484 | 2026-05-01 | D | 58 | CN006UD6705-1 | 001 | SW12 | LAMINATION | SW | 4
485 | 2026-05-02 | D | 58 | CN006UD6675-3 | 003 | SW01 | ADHESIVE JOINT | SW | 4 | 7
486 | 2026-05-02 | D | 58 | CN006UD6675-8 | 008 | SW07 | ADHESIVE JOINT | SW | 4
487 | 2026-05-02 | D | 58 | CN006UD6695-1 | 001 | SW03 | ADHESIVE JOINT | SW | 4
488 | 2026-05-02 | D | 58 | CN006UD6743-2 | 002 | SW02 | ADHESIVE JOINT | SW | 4
489 | 2026-05-02 | D | 58 | CN006UD8649-1 | 001 | SW02 | ADHESIVE JOINT | SW | 4
490 | 2026-05-02 | D | 58 | CN006UD8649-1 | 001 | SW05 | ADHESIVE JOINT | SW | 4
491 | 2026-05-02 | D | 58 | CN006UD8650-1 | 001 | SW02 | ADHESIVE JOINT | SW | 4
492 | 2026-05-02 | D | 58 | CN006UD8650-1 | 001 | SW03 | ADHESIVE JOINT | SW | 4
493 | 2026-05-02 | D | 58 | CN006UD6683-1 | 001 | SW01 | ADHESIVE JOINT | SW | 4
494 | 2026-05-02 | D | 58 | CN006UD6683-1 | 001 | SW02 | ADHESIVE JOINT | SW | 4
495 | 2026-05-02 | D | 58 | CN006UD6675-11 | 011 | SW10 | LAMINATION | SW | 4
496 | 2026-05-02 | D | 58 | CN006UD6675-14 | 014 | SW02 | LAMINATION | SW | 4
497 | 2026-05-02 | D | 58 | CN006UD6705-1 | 001 | SW01 | LAMINATION | SW | 4
498 | 2026-05-02 | D | 58 | CN006UD6705-1 | 001 | SW02 | LAMINATION | SW | 4
499 | 2026-05-02 | D | 58 | CN006UD6675-7 | 007 | SW11 | LAMINATION | SW | 4
500 | 2026-05-02 | D | 58 | CN006UD6675-7 | 007 | SW12 | LAMINATION | SW | 4
501 | 2026-05-02 | D | 58 | CN006UD6743-2 | 002 | SW01 | LAMINATION | SW | 4
502 | 2026-05-02 | D | 58 | CN006UD6743-2 | 002 | SW03 | LAMINATION | SW | 4
503 | 2026-05-02 | D | 58 | CN006UD6743-2 | 002 | SW12 | LAMINATION | SW | 4
504 | 2026-05-02 | D | 58 | CN006UD6743-4 | 004 | SW07 | LAMINATION | SW | 4
505 | 2026-05-04 | D | 58 | CN006UD6675-14 | 014 | SW01 | LAMINATION | SW | 4 | 7
506 | 2026-05-04 | D | 58 | CN006UD6675-3 | 003 | SW01 | LAMINATION | SW | 4
507 | 2026-05-04 | D | 58 | CN006UD6675-3 | 003 | SW02 | LAMINATION | SW | 4
508 | 2026-05-04 | D | 58 | CN006UD6675-8 | 008 | SW07 | LAMINATION | SW | 4
509 | 2026-05-04 | D | 58 | CN006UD6701-1 | 001 | SW05 | LAMINATION | SW | 4
510 | 2026-05-04 | D | 58 | CN006UD6743-2 | 002 | SW02 | LAMINATION | SW | 4
511 | 2026-05-04 | D | 58 | CN006UD8649-1 | 001 | SW05 | LAMINATION | SW | 4
512 | 2026-05-04 | D | 58 | CN006UD8650-1 | 001 | SW01 | LAMINATION | SW | 4
513 | 2026-05-04 | D | 58 | CN006UD8650-1 | 001 | SW02 | LAMINATION | SW | 4
514 | 2026-05-04 | D | 58 | CN006UD8650-1 | 001 | SW03 | LAMINATION | SW | 4
515 | 2026-05-04 | D | 58 | CN006UD6675-12 | 012 | SW01 | ADHESIVE JOINT | SW | 4
516 | 2026-05-04 | D | 58 | CN006UD6675-8 | 008 | SW02 | ADHESIVE JOINT | SW | 4
517 | 2026-05-04 | D | 58 | CN006UD6696-1 | 001 | SW01 | ADHESIVE JOINT | SW | 4
518 | 2026-05-04 | D | 58 | CN006UD6696-1 | 001 | SW03 | ADHESIVE JOINT | SW | 4
519 | 2026-05-04 | D | 58 | CN006UD6743-1 | 001 | SW01 | ADHESIVE JOINT | SW | 4
520 | 2026-05-04 | D | 58 | CN006UD6743-2 | 002 | SW07 | ADHESIVE JOINT | SW | 4
521 | 2026-05-04 | D | 58 | CN006UD6743-3 | 003 | SW01 | ADHESIVE JOINT | SW | 4
522 | 2026-05-04 | D | 58 | CN006UD6743-3 | 003 | SW04 | ADHESIVE JOINT | SW | 4
523 | 2026-05-04 | D | 58 | CN006UD8649-1 | 001 | SW03 | ADHESIVE JOINT | SW | 4
524 | 2026-05-04 | D | 58 | CN006UD6768-1 | 001 | SW09 | ADHESIVE JOINT | SW | 4
525 | 2026-05-05 | D | 58 | CN006UD6675-13 | 013 | SW01 | LAMINATION | SW | 4 | 7
526 | 2026-05-05 | D | 58 | CN006UD6675-13 | 013 | SW02 | LAMINATION | SW | 4
527 | 2026-05-05 | D | 58 | CN006UD6675-2 | 002 | SW08 | LAMINATION | SW | 4
528 | 2026-05-05 | D | 58 | CN006UD6675-3 | 003 | SW09 | LAMINATION | SW | 4
529 | 2026-05-05 | D | 58 | CN006UD6695-1 | 001 | SW01 | LAMINATION | SW | 4
530 | 2026-05-05 | D | 58 | CN006UD6695-1 | 001 | SW02 | LAMINATION | SW | 4
531 | 2026-05-05 | D | 58 | CN006UD6695-1 | 001 | SW03 | LAMINATION | SW | 4
532 | 2026-05-05 | D | 58 | CN006UD8649-1 | 001 | SW01 | LAMINATION | SW | 4
533 | 2026-05-05 | D | 58 | CN006UD8649-1 | 001 | SW02 | LAMINATION | SW | 4
534 | 2026-05-05 | D | 58 | CN006UD8649-1 | 001 | SW03 | LAMINATION | SW | 4
535 | 2026-05-05 | D | 58 | CN006UD6675-12 | 012 | SW02 | ADHESIVE JOINT | SW | 4
536 | 2026-05-05 | D | 58 | CN006UD6696-1 | 001 | SW02 | ADHESIVE JOINT | SW | 4
537 | 2026-05-05 | D | 58 | CN006UD6696-1 | 001 | SW05 | ADHESIVE JOINT | SW | 4
538 | 2026-05-05 | D | 58 | CN006UD6701-1 | 001 | SW04 | ADHESIVE JOINT | SW | 4
539 | 2026-05-05 | D | 58 | CN006UD6743-1 | 001 | SW02 | ADHESIVE JOINT | SW | 4
540 | 2026-05-05 | D | 58 | CN006UD6743-1 | 001 | SW04 | ADHESIVE JOINT | SW | 4
541 | 2026-05-05 | D | 58 | CN006UD6743-3 | 003 | SW02 | ADHESIVE JOINT | SW | 4
542 | 2026-05-05 | D | 58 | CN006UD6743-3 | 003 | SW03 | ADHESIVE JOINT | SW | 4
543 | 2026-05-05 | D | 58 | CN006UD6743-3 | 003 | SW06 | ADHESIVE JOINT | SW | 4
544 | 2026-05-05 | D | 58 | CN006UD6683-1 | 001 | SW07 | ADHESIVE JOINT | SW | 4
545 | 2026-05-06 | D | 58 | CN006UD6675-8 | 008 | SW01 | LAMINATION | SW | 4 | 6
546 | 2026-05-06 | D | 58 | CN006UD6675-8 | 008 | SW02 | LAMINATION | SW | 4
547 | 2026-05-06 | D | 58 | CN006UD6696-1 | 001 | SW01 | LAMINATION | SW | 4
548 | 2026-05-06 | D | 58 | CN006UD6696-1 | 001 | SW02 | LAMINATION | SW | 4
549 | 2026-05-06 | D | 58 | CN006UD6696-1 | 001 | SW03 | LAMINATION | SW | 4
550 | 2026-05-06 | D | 58 | CN006UD6743-1 | 001 | SW01 | LAMINATION | SW | 4
551 | 2026-05-06 | D | 58 | CN006UD6743-1 | 001 | SW02 | LAMINATION | SW | 4
552 | 2026-05-06 | D | 58 | CN006UD6743-1 | 001 | SW04 | LAMINATION | SW | 4
553 | 2026-05-06 | D | 58 | CN006UD6743-3 | 003 | SW01 | LAMINATION | SW | 4
554 | 2026-05-06 | D | 58 | CN006UD6743-3 | 003 | SW02 | LAMINATION | SW | 4
555 | 2026-05-06 | D | 58 | CN006UD6743-3 | 003 | SW03 | LAMINATION | SW | 4
556 | 2026-05-06 | D | 58 | CN006UD6743-3 | 003 | SW04 | LAMINATION | SW | 4
557 | 2026-05-06 | D | 58 | CN006UD6743-3 | 003 | SW14 | LAMINATION | SW | 4
558 | 2026-05-06 | D | 58 | CN006UD6683-1 | 001 | SW01 | LAMINATION | SW | 4
559 | 2026-05-06 | D | 58 | CN006UD6683-1 | 001 | SW02 | LAMINATION | SW | 4
560 | 2026-05-06 | D | 58 | CN006UD6707-1 | 001 | SW04 | ADHESIVE JOINT | SW | 4
561 | 2026-05-06 | D | 58 | CN006UD6743-1 | 001 | SW06 | ADHESIVE JOINT | SW | 4
562 | 2026-05-06 | D | 58 | CN006UD6743-2 | 002 | SW11 | ADHESIVE JOINT | SW | 4
563 | 2026-05-06 | D | 58 | CN006UD6743-3 | 003 | SW16 | ADHESIVE JOINT | SW | 4
564 | 2026-05-06 | D | 58 | CN006UD6743-4 | 004 | SW01 | ADHESIVE JOINT | SW | 4
565 | 2026-05-07 | D | 58 | CN006UD6675-1 | 001 | SW03 | LAMINATION | SW | 4 | 6
566 | 2026-05-07 | D | 58 | CN006UD6675-1 | 001 | SW04 | LAMINATION | SW | 4
567 | 2026-05-07 | D | 58 | CN006UD6675-12 | 012 | SW01 | LAMINATION | SW | 4
568 | 2026-05-07 | D | 58 | CN006UD6675-12 | 012 | SW02 | LAMINATION | SW | 4
569 | 2026-05-07 | D | 58 | CN006UD6675-2 | 002 | SW11 | LAMINATION | SW | 4
570 | 2026-05-07 | D | 58 | CN006UD6675-6 | 006 | SW02 | LAMINATION | SW | 4
571 | 2026-05-07 | D | 58 | CN006UD6675-7 | 007 | SW10 | LAMINATION | SW | 4
572 | 2026-05-07 | D | 58 | CN006UD6701-1 | 001 | SW04 | LAMINATION | SW | 4
573 | 2026-05-07 | D | 58 | CN006UD6743-2 | 002 | SW11 | LAMINATION | SW | 4
574 | 2026-05-07 | D | 58 | CN006UD6743-4 | 004 | SW01 | LAMINATION | SW | 4
575 | 2026-05-07 | D | 58 | CN006UD6743-1 | 001 | SW08 | ADHESIVE JOINT | SW | 4
576 | 2026-05-07 | D | 58 | CN006UD8650-1 | 001 | SW05 | ADHESIVE JOINT | SW | 4
577 | 2026-05-07 | D | 58 | CN006UD6693-1 | 001 | SW01 | ADHESIVE JOINT | SW | 4
578 | 2026-05-07 | D | 58 | CN006UD6693-1 | 001 | SW03 | ADHESIVE JOINT | SW | 4
579 | 2026-05-07 | D | 58 | CN006UD6693-1 | 001 | SW05 | ADHESIVE JOINT | SW | 4
580 | 2026-05-07 | D | 58 | CN006UD6693-1 | 001 | SW07 | ADHESIVE JOINT | SW | 4
581 | 2026-05-07 | D | 58 | CN006UD6693-1 | 001 | SW10 | ADHESIVE JOINT | SW | 4
582 | 2026-05-07 | D | 58 | CN006UD6693-1 | 001 | SW13 | ADHESIVE JOINT | SW | 4
583 | 2026-05-08 | FW | 58 | CN007UFW2458-1 | 001 | SW04 | LAMINATION | SW | 8 | 10
584 | 2026-05-08 | FW | 58 | CN007UFW2458-1 | 001 | SW05 | LAMINATION | SW | 8
585 | 2026-05-08 | FW | 58 | CN007UFW2458-1 | 001 | SW06 | LAMINATION | SW | 8
586 | 2026-05-08 | FW | 58 | CN002UFW2457-1 | 001 | SW03 | LAMINATION | SW | 8
587 | 2026-05-08 | FW | 58 | CN002UFW2457-1 | 001 | SW04 | LAMINATION | SW | 8
588 | 2026-05-08 | FW | 58 | CN006UFW2366-1 | 001 | SW03 | LAMINATION | SW | 8
589 | 2026-05-08 | FW | 58 | CN006UFW2366-1 | 001 | SW05 | LAMINATION | SW | 8
590 | 2026-05-08 | FW | 58 | CN006UFW2366-2 | 002 | SW15 | LAMINATION | SW | 8
591 | 2026-05-08 | D | 58 | CN006UD6747-2 | 002 | SW01 | ADHESIVE JOINT | SW | 4
592 | 2026-05-08 | D | 58 | CN006UD6747-2 | 002 | SW02 | ADHESIVE JOINT | SW | 4
593 | 2026-05-08 | D | 58 | CN006UD6693-1 | 001 | SW02 | ADHESIVE JOINT | SW | 4
594 | 2026-05-08 | D | 58 | CN006UD6693-1 | 001 | SW09 | ADHESIVE JOINT | SW | 4
595 | 2026-05-08 | D | 58 | CN006UD6693-1 | 001 | SW11 | ADHESIVE JOINT | SW | 4
596 | 2026-05-08 | D | 58 | CN002UD6965-1 | 001 | SW05 | ADHESIVE JOINT | SW | 4
597 | 2026-05-08 | D | 58 | CN002UD6965-1 | 001 | SW07 | ADHESIVE JOINT | SW | 4
598 | 2026-05-08 | D | 58 | CN002UD6965-1 | 001 | SW11 | ADHESIVE JOINT | SW | 4
599 | 2026-05-08 | D | 58 | CN002UD6965-1 | 001 | SW13 | ADHESIVE JOINT | SW | 4
600 | 2026-05-08 | D | 58 | CN002UD6965-1 | 001 | SW14 | ADHESIVE JOINT | SW | 4
601 | 2026-05-09 | FW | 58 | CN006UFW2366-1 | 001 | SW01 | LAMINATION | SW | 4 | 10
602 | 2026-05-09 | FW | 58 | CN006UFW2366-1 | 001 | SW02 | LAMINATION | SW | 4
603 | 2026-05-09 | FW | 58 | CN006UFW2361-1 | 001 | SW09 | LAMINATION | SW | 4
604 | 2026-05-09 | FW | 58 | CN006UFW2361-1 | 001 | SW13 | LAMINATION | SW | 4
605 | 2026-05-09 | D | 58 | CN006UD6696-1 | 001 | SW05 | LAMINATION | SW | 4
606 | 2026-05-09 | D | 58 | CN006UD6743-2 | 002 | SW07 | LAMINATION | SW | 4
607 | 2026-05-09 | D | 58 | CN006UD8650-1 | 001 | SW05 | LAMINATION | SW | 4
608 | 2026-05-09 | D | 58 | CN006UD6693-1 | 001 | SW01 | LAMINATION | SW | 4
609 | 2026-05-09 | D | 58 | CN006UD6693-1 | 001 | SW02 | LAMINATION | SW | 4
610 | 2026-05-09 | D | 58 | CN006UD6693-1 | 001 | SW03 | LAMINATION | SW | 4
611 | 2026-05-09 | D | 58 | CN006UD6693-1 | 001 | SW05 | LAMINATION | SW | 4
612 | 2026-05-09 | D | 58 | CN006UD6693-1 | 001 | SW07 | LAMINATION | SW | 4
613 | 2026-05-09 | D | 58 | CN006UD6693-1 | 001 | SW09 | LAMINATION | SW | 4
614 | 2026-05-09 | D | 58 | CN006UD6693-1 | 001 | SW10 | LAMINATION | SW | 4
615 | 2026-05-09 | D | 58 | CN006UD6693-1 | 001 | SW11 | LAMINATION | SW | 4
616 | 2026-05-09 | D | 58 | CN002UD6965-1 | 001 | SW05 | LAMINATION | SW | 4
617 | 2026-05-09 | D | 58 | CN002UD6965-1 | 001 | SW07 | LAMINATION | SW | 4
618 | 2026-05-09 | D | 58 | CN002UD6965-1 | 001 | SW11 | LAMINATION | SW | 4
619 | 2026-05-09 | D | 58 | CN002UD6965-1 | 001 | SW13 | LAMINATION | SW | 4
620 | 2026-05-09 | D | 58 | CN006UD6743-2 | 002 | SW05 | ADHESIVE JOINT | SW | 4
621 | 2026-05-09 | D | 58 | CN006UD6747-2 | 002 | SW03 | ADHESIVE JOINT | SW | 4
622 | 2026-05-09 | D | 58 | CN006UD6747-2 | 002 | SW04 | ADHESIVE JOINT | SW | 4
623 | 2026-05-09 | D | 58 | CN006UD6747-2 | 002 | SW16 | ADHESIVE JOINT | SW | 4
624 | 2026-05-09 | D | 58 | CN006UD6693-1 | 001 | SW15 | ADHESIVE JOINT | SW | 4
625 | 2026-05-09 | D | 58 | CN002UD6965-1 | 001 | SW01 | ADHESIVE JOINT | SW | 4
626 | 2026-05-09 | D | 58 | CN002UD6965-1 | 001 | SW03 | ADHESIVE JOINT | SW | 4
627 | 2026-05-09 | D | 58 | CN002UD6965-1 | 001 | SW15 | ADHESIVE JOINT | SW | 4
628 | 2026-05-09 | D | 58 | CN002UD6965-1 | 001 | SW17 | ADHESIVE JOINT | SW | 4
629 | 2026-05-09 | D | 58 | CN002UD6965-1 | 001 | SW21 | ADHESIVE JOINT | SW | 4
630 | 2026-05-11 | D | 58 | CN006UD6675-1 | 001 | SW06 | LAMINATION | SW | 4 | 9
631 | 2026-05-11 | FW | 58 | CN006UFW2366-4 | 004 | SW03 | LAMINATION | SW | 8
632 | 2026-05-11 | D | 58 | CN006UD6707-1 | 001 | SW04 | LAMINATION | SW | 4
633 | 2026-05-11 | D | 58 | CN006UD6743-1 | 001 | SW06 | LAMINATION | SW | 4
634 | 2026-05-11 | D | 58 | CN006UD6743-1 | 001 | SW08 | LAMINATION | SW | 4
635 | 2026-05-11 | D | 58 | CN006UD6743-2 | 002 | SW05 | LAMINATION | SW | 4
636 | 2026-05-11 | D | 58 | CN006UD6743-3 | 003 | SW16 | LAMINATION | SW | 4
637 | 2026-05-11 | D | 58 | CN006UD6747-2 | 002 | SW01 | LAMINATION | SW | 4
638 | 2026-05-11 | D | 58 | CN006UD6747-2 | 002 | SW02 | LAMINATION | SW | 4
639 | 2026-05-11 | D | 58 | CN006UD6747-2 | 002 | SW03 | LAMINATION | SW | 4
640 | 2026-05-11 | D | 58 | CN006UD6747-2 | 002 | SW04 | LAMINATION | SW | 4
641 | 2026-05-11 | D | 58 | CN006UD6747-2 | 002 | SW16 | LAMINATION | SW | 4
642 | 2026-05-11 | D | 58 | CN006UD6768-1 | 001 | SW09 | LAMINATION | SW | 4
643 | 2026-05-11 | D | 58 | CN006UD6693-1 | 001 | SW13 | LAMINATION | SW | 4
644 | 2026-05-11 | D | 58 | CN002UD6965-1 | 001 | SW13 | LAMINATION | SW | 4
645 | 2026-05-11 | D | 58 | CN002UD6965-1 | 001 | SW14 | LAMINATION | SW | 4
646 | 2026-05-11 | D | 58 | CN002UD6965-1 | 001 | SW15 | LAMINATION | SW | 4
647 | 2026-05-11 | D | 58 | CN002UD6965-1 | 001 | SW21 | LAMINATION | SW | 4
648 | 2026-05-11 | D | 58 | CN006UD6768-1 | 001 | SW01 | ADHESIVE JOINT | SW | 4
649 | 2026-05-11 | D | 58 | CN006UD6768-1 | 001 | SW02 | ADHESIVE JOINT | SW | 4
650 | 2026-05-11 | D | 58 | CN006UD6768-1 | 001 | SW04 | ADHESIVE JOINT | SW | 4
651 | 2026-05-11 | D | 58 | CN006UD6768-1 | 001 | SW06 | ADHESIVE JOINT | SW | 4
652 | 2026-05-11 | D | 58 | CN006UD6768-1 | 001 | SW08 | ADHESIVE JOINT | SW | 4
653 | 2026-05-11 | D | 58 | CN006UD6765-1 | 001 | SW05 | ADHESIVE JOINT | SW | 4
654 | 2026-05-11 | D | 58 | CN006UD6747-1 | 001 | SW07 | ADHESIVE JOINT | SW | 4
655 | 2026-05-11 | D | 58 | CN002UD6965-1 | 001 | SW02 | ADHESIVE JOINT | SW | 4
656 | 2026-05-11 | D | 58 | CN002UD6965-1 | 001 | SW19 | ADHESIVE JOINT | SW | 4
657 | 2026-05-11 | D | 58 | CN002UD6965-1 | 001 | SW22 | ADHESIVE JOINT | SW | 4
658 | 2026-05-12 | FW | 58 | CN006UFW2366-3 | 003 | SW06 | LAMINATION | SW | 8 | 9
659 | 2026-05-12 | FW | 58 | CN006UFW2361-1 | 001 | SW07 | LAMINATION | SW | 8
660 | 2026-05-12 | D | 58 | CN006UD6743-3 | 003 | SW06 | LAMINATION | SW | 4
661 | 2026-05-12 | D | 58 | CN006UD6768-1 | 001 | SW01 | LAMINATION | SW | 4
662 | 2026-05-12 | D | 58 | CN006UD6768-1 | 001 | SW02 | LAMINATION | SW | 4
663 | 2026-05-12 | D | 58 | CN006UD6768-1 | 001 | SW04 | LAMINATION | SW | 4
664 | 2026-05-12 | D | 58 | CN006UD6768-1 | 001 | SW06 | LAMINATION | SW | 4
665 | 2026-05-12 | D | 58 | CN006UD6768-1 | 001 | SW08 | LAMINATION | SW | 4
666 | 2026-05-12 | D | 58 | CN006UD6693-1 | 001 | SW15 | LAMINATION | SW | 4
667 | 2026-05-12 | D | 58 | CN002UD6965-1 | 001 | SW01 | LAMINATION | SW | 4
668 | 2026-05-12 | D | 58 | CN002UD6965-1 | 001 | SW03 | LAMINATION | SW | 4
669 | 2026-05-12 | D | 58 | CN002UD6965-1 | 001 | SW17 | LAMINATION | SW | 4
670 | 2026-05-12 | D | 58 | CN002UD6965-1 | 001 | SW02 | LAMINATION | SW | 4
671 | 2026-05-12 | D | 58 | CN002UD6965-1 | 001 | SW19 | LAMINATION | SW | 4
672 | 2026-05-12 | D | 58 | CN002UD6965-1 | 001 | SW22 | LAMINATION | SW | 4
673 | 2026-05-12 | D | 58 | CN006UD6765-1 | 001 | SW05 | LAMINATION | SW | 4
674 | 2026-05-12 | D | 58 | CN006UD6747-1 | 001 | SW04 | ADHESIVE JOINT | SW | 4
675 | 2026-05-12 | D | 58 | CN006UD6747-1 | 001 | SW06 | ADHESIVE JOINT | SW | 4
676 | 2026-05-12 | D | 58 | CN006UD6747-1 | 001 | SW13 | ADHESIVE JOINT | SW | 4
677 | 2026-05-12 | D | 58 | CN006UD6693-2 | 002 | SW01 | ADHESIVE JOINT | SW | 4
678 | 2026-05-12 | D | 58 | CN006UD6693-2 | 002 | SW04 | ADHESIVE JOINT | SW | 4
679 | 2026-05-12 | D | 58 | CN006UD6693-2 | 002 | SW12 | ADHESIVE JOINT | SW | 4
680 | 2026-05-12 | D | 58 | CN006UD6693-2 | 002 | SW14 | ADHESIVE JOINT | SW | 4
681 | 2026-05-12 | D | 58 | CN006UD6693-3 | 003 | SW05 | ADHESIVE JOINT | SW | 4
682 | 2026-05-12 | D | 58 | CN006UD6693-3 | 003 | SW08 | ADHESIVE JOINT | SW | 4
683 | 2026-05-12 | D | 58 | CN006UD6693-3 | 003 | SW13 | ADHESIVE JOINT | SW | 4
684 | 2026-05-13 | D | 58 | CN006UD6747-1 | 001 | SW06 | LAMINATION | SW | 4 | 10
685 | 2026-05-13 | D | 58 | CN006UD6747-1 | 001 | SW07 | LAMINATION | SW | 4
686 | 2026-05-13 | D | 58 | CN006UD6747-1 | 001 | SW13 | LAMINATION | SW | 4
687 | 2026-05-13 | D | 58 | CN006UD6693-2 | 002 | SW01 | LAMINATION | SW | 4
688 | 2026-05-13 | D | 58 | CN006UD6693-2 | 002 | SW04 | LAMINATION | SW | 4
689 | 2026-05-13 | D | 58 | CN006UD6693-2 | 002 | SW12 | LAMINATION | SW | 4
690 | 2026-05-13 | D | 58 | CN006UD6693-2 | 002 | SW14 | LAMINATION | SW | 4
691 | 2026-05-13 | D | 58 | CN006UD6693-3 | 003 | SW05 | LAMINATION | SW | 4
692 | 2026-05-13 | D | 58 | CN006UD6693-3 | 003 | SW13 | LAMINATION | SW | 4
693 | 2026-05-13 | D | 58 | CN002UD6965-1 | 001 | SW09 | LAMINATION | SW | 4
694 | 2026-05-13 | D | 58 | CN002UD6965-1 | 001 | SW09 | ADHESIVE JOINT | SW | 4
695 | 2026-05-13 | FW | 58 | CN006UFW2366-4 | 004 | SW06 | ADHESIVE JOINT | SW | 12
696 | 2026-05-13 | FW | 58 | CN006UFW2366-4 | 004 | SW07 | ADHESIVE JOINT | SW | 12
697 | 2026-05-13 | FW | 58 | CN006UFW2366-4 | 004 | SW08 | ADHESIVE JOINT | SW | 12
698 | 2026-05-13 | FW | 58 | CN006UFW2366-4 | 004 | SW09 | ADHESIVE JOINT | SW | 12
699 | 2026-05-13 | FW | 58 | CN006UFW2366-4 | 004 | SW10 | ADHESIVE JOINT | SW | 12
700 | 2026-05-14 | FW | 58 | CN006UFW2366-2 | 002 | SW02 | ADHESIVE JOINT | SW | 12 | 10
701 | 2026-05-14 | FW | 58 | CN006UFW2366-2 | 002 | SW03 | ADHESIVE JOINT | SW | 12
702 | 2026-05-14 | FW | 58 | CN006UFW2366-2 | 002 | SW06 | ADHESIVE JOINT | SW | 12
703 | 2026-05-14 | FW | 58 | CN006UFW2366-2 | 002 | SW08 | ADHESIVE JOINT | SW | 12
704 | 2026-05-14 | FW | 58 | CN006UFW2366-1 | 001 | SW21 | ADHESIVE JOINT | SW | 12
705 | 2026-05-14 | FW | 58 | CN006UFW2366-4 | 004 | SW06 | LAMINATION | SW | 12
706 | 2026-05-14 | FW | 58 | CN006UFW2366-4 | 004 | SW07 | LAMINATION | SW | 12
707 | 2026-05-14 | FW | 58 | CN006UFW2366-4 | 004 | SW08 | LAMINATION | SW | 12
708 | 2026-05-14 | FW | 58 | CN006UFW2366-4 | 004 | SW09 | LAMINATION | SW | 12
709 | 2026-05-14 | FW | 58 | CN006UFW2366-4 | 004 | SW10 | LAMINATION | SW | 12
710 | 2026-05-15 | FW | 58 | CN006UFW2366-2 | 002 | SW06 | LAMINATION | SW | 12 | 7 | HEAVY SANDSTORM AFTER LUNCH
711 | 2026-05-15 | FW | 58 | CN006UFW2366-2 | 002 | SW08 | LAMINATION | SW | 12
712 | 2026-05-15 | FW | 58 | CN006UFW2366-1 | 001 | SW19 | ADHESIVE JOINT | SW | 12
713 | 2026-05-15 | FW | 58 | CN006UFW2366-1 | 001 | SW20 | ADHESIVE JOINT | SW | 12
714 | 2026-05-16 | FW | 58 | CN006UFW2366-1 | 001 | SW20 | LAMINATION | SW | 12 | 10 | PIPE TRANSFERRED TO SITE FOR AOC LINE
715 | 2026-05-16 | FW | 58 | CN006UFW2366-1 | 001 | SW21 | LAMINATION | SW | 12
716 | 2026-05-16 | FW | 58 | CN006UFW2366-2 | 002 | SW02 | LAMINATION | SW | 12
717 | 2026-05-16 | FW | 58 | CN006UFW2366-2 | 002 | SW03 | LAMINATION | SW | 12
718 | 2026-05-16 | FW | 58 | CN006UFW2366-1 | 001 | SW13 | ADHESIVE JOINT | SW | 12
719 | 2026-05-16 | FW | 58 | CN006UFW2366-1 | 001 | SW17 | ADHESIVE JOINT | SW | 12
720 | 2026-05-16 | FW | 58 | CN006UFW2366-1 | 001 | SW18 | ADHESIVE JOINT | SW | 12
721 | 2026-05-16 | FW | 58 | CN006UFW2366-3 | 003 | SW10 | ADHESIVE JOINT | SW | 12
722 | 2026-05-16 | FW | 58 | CN006UFW2366-3 | 003 | SW11 | ADHESIVE JOINT | SW | 12
723 | 2026-05-18 | FW | 58 | CN006UFW2366-1 | 001 | SW13 | LAMINATION | SW | 12 | 10
724 | 2026-05-18 | FW | 58 | CN006UFW2366-1 | 001 | SW18 | LAMINATION | SW | 12
725 | 2026-05-18 | FW | 58 | CN006UFW2366-1 | 001 | SW19 | LAMINATION | SW | 12
726 | 2026-05-18 | FW | 58 | CN006UFW2366-3 | 003 | SW10 | LAMINATION | SW | 12
727 | 2026-05-18 | FW | 58 | CN006UFW2366-3 | 003 | SW11 | LAMINATION | SW | 12
728 | 2026-05-19 | D | 58 | CN006UD6747-2 | 002 | SW11 | ADHESIVE JOINT | SW | 4 | 10 | HEAVY SANDSTORM AFTER LUNCH NO LAMINATION IN YARD DUE TO THE ABSENCE OF ADPF SUPERVISOR
729 | 2026-05-19 | D | 58 | CN006UD6747-1 | 001 | SW16 | ADHESIVE JOINT | SW | 4
730 | 2026-05-19 | D | 58 | CN006UD6693-2 | 002 | SW02 | ADHESIVE JOINT | SW | 4
731 | 2026-05-19 | D | 58 | CN006UD6693-2 | 002 | SW13 | ADHESIVE JOINT | SW | 4
732 | 2026-05-19 | D | 58 | CN006UD6693-3 | 003 | SW02 | ADHESIVE JOINT | SW | 4
733 | 2026-05-19 | D | 58 | CN006UD6693-3 | 003 | SW11 | ADHESIVE JOINT | SW | 4
734 | 2026-05-20 | D | 58 | CN006UD6693-2 | 002 | SW10 | ADHESIVE JOINT | SW | 4 | 10 | NO LAMINATION IN YARD DUE TO THE ABSENCE OF ADPF SUPERVISOR
735 | 2026-05-20 | FW | 58 | CN002UFW2375-5 | 005 | SW05 | ADHESIVE JOINT | SW | 12
736 | 2026-05-20 | FW | 58 | CN002UFW2375-5 | 005 | SW07 | ADHESIVE JOINT | SW | 12
737 | 2026-05-20 | FW | 58 | CN007UFW2375-6 | 006 | SW02 | ADHESIVE JOINT | SW | 12
738 | 2026-05-20 | AOC | 58 |  |  |  | ADHESIVE JOINT | FW | 20 |  | ISOMETRIC DRAWING NOT RECEIVED
739 | 2026-05-21 | FW | 58 | CN007UFW2375-4 | 004 | SW02 | ADHESIVE JOINT | SW | 12 | 10 | NO LAMINATION IN YARD DUE TO THE ABSENCE OF ADPF SUPERVISOR
740 | 2026-05-21 | FW | 58 | CN002UFW2375-3 | 003 | SW02 | ADHESIVE JOINT | SW | 12
741 | 2026-05-21 | FW | 58 | CN002UFW2375-4 | 004 | SW02 | ADHESIVE JOINT | SW | 12
742 | 2026-05-21 | FW | 58 | CN002UFW2375-5 | 005 | SW06 | ADHESIVE JOINT | SW | 12
743 | 2026-05-21 | AOC | 58 |  |  |  | ADHESIVE JOINT | FW | 20 |  | ISOMETRIC DRAWING NOT RECEIVED
744 | 2026-05-21 | AOC | 58 |  |  |  | ADHESIVE JOINT | FW | 20
745 | 2026-05-22 | AOC | 58 |  |  |  | LAMINATION | FW | 20 | 9 | ISOMETRIC DRAWING NOT RECEIVED
746 | 2026-05-22 | D | 58 | CN006UD6693-3 | 003 | SW11 | LAMINATION | SW | 4
747 | 2026-05-22 | FW | 58 | CN002UFW2375-5 | 005 | SW05 | LAMINATION | SW | 12
748 | 2026-05-22 | FW | 58 | CN002UFW2375-5 | 005 | SW06 | LAMINATION | SW | 12
749 | 2026-05-22 | FW | 58 | CN002UFW2375-5 | 005 | SW07 | LAMINATION | SW | 12
750 | 2026-05-22 | FW | 58 | CN007UFW2375-6 | 006 | SW02 | LAMINATION | SW | 12
751 | 2026-05-22 | FW | 58 | CN002UFW2375-4 | 004 | SW02 | LAMINATION | SW | 12
752 | 2026-05-23 | AOC | 58 |  |  |  | LAMINATION | FW | 20 | 10 | ISOMETRIC DRAWING NOT RECEIVED CUTTING AND GRINDING FOR 3" BUILDUP-YARD
753 | 2026-05-23 | AOC | 58 |  |  |  | LAMINATION | FW | 20
754 | 2026-05-23 | AOC | 58 |  |  |  | ADHESIVE JOINT | FW | 20
755 | 2026-05-25 | AOC | 58 |  |  |  | LAMINATION | FW | 20 | 10 | ISOMETRIC DRAWING NOT RECEIVED CUTTING AND GRINDING FOR 3" BUILDUP-YARD
756 | 2026-05-25 | AOC | 58 |  |  |  | LAMINATION | FW | 20
757 | 2026-05-25 | AOC | 58 |  |  |  | ADHESIVE JOINT | FW | 20
758 | 2026-05-29 | AOC | 58 |  |  |  | ADHESIVE JOINT | FW | 20 | 4 | ISOMETRIC DRAWING NOT RECEIVED
759 | 2026-05-29 | AOC | 58 |  |  |  | LAMINATION | FW | 20
760 | 2026-05-30 | D | 58 | CN006UD6747-2 | 002 | SW11 | LAMINATION | SW | 4 | 9 | SITE ACTIVITY- HEATING ONLY
761 | 2026-05-30 | D | 58 | CN006UD6747-1 | 001 | SW16 | LAMINATION | SW | 4 |  | BUILDUP 3"- 38 JOINTS
762 | 2026-05-30 | D | 58 | CN006UD6693-2 | 002 | SW02 | LAMINATION | SW | 4
763 | 2026-05-30 | D | 58 | CN006UD6693-2 | 002 | SW13 | LAMINATION | SW | 4
764 | 2026-05-30 | D | 58 | CN006UD6693-3 | 003 | SW02 | LAMINATION | SW | 4
765 | 2026-05-30 | D | 58 | CN006UD6693-3 | 003 | SW11 | LAMINATION | SW | 4
766 | 2026-05-30 | FW | 58 | CN007UFW2375-4 | 004 | SW02 | LAMINATION | SW | 12
767 | 2026-05-30 | FW | 58 | CN007UFW2375-3 | 003 | SW02 | LAMINATION | SW | 12
768 | 2026-05-30 | FW | 58 | CN007UFW2375-4 | 001 | SW01 | ADHESIVE JOINT | SW | 12
769 | 2026-06-01 | FW | 58 | CN007UFW2375-3 | 003 | SW07 | ADHESIVE JOINT | SW | 12 | 9 | SITE ACTIVITY- HEATING ONLY
770 | 2026-06-01 | FW | 58 | CN007UFW2375-5 | 005 | SW05 | ADHESIVE JOINT | SW | 12
771 | 2026-06-01 | FW | 58 | CN002UD8669-1 | 001 | SW09 | ADHESIVE JOINT | SW | 4
772 | 2026-06-01 | FW | 58 | CN006UD6693-4 | 004 | SW12 | ADHESIVE JOINT | SW | 4
773 | 2026-06-01 | FW | 58 | CN002UD6982-3 | 003 | SW10 | ADHESIVE JOINT | SW | 4
774 | 2026-06-01 | FW | 58 | CN007UFW2375-4 | 004 | SW01 | LAMINATION | SW | 12
775 | 2026-06-02 | D | 58 | CN002UD8669-1 | 001 | SW05 | ADHESIVE JOINT | SW | 4 | 9 | SITE ACTIVITY- HEATING ONLY
776 | 2026-06-02 | D | 58 | CN002UD8669-1 | 001 | SW07 | ADHESIVE JOINT | SW | 4
777 | 2026-06-02 | D | 58 | CN006UD6693-4 | 004 | SW05 | ADHESIVE JOINT | SW | 4
778 | 2026-06-02 | D | 58 | CN006UD6693-4 | 004 | SW08 | ADHESIVE JOINT | SW | 4
779 | 2026-06-02 | D | 58 | CN006UD6693-4 | 004 | SW10 | ADHESIVE JOINT | SW | 4
780 | 2026-06-02 | D | 58 | CN002UD6982-3 | 003 | SW01 | ADHESIVE JOINT | SW | 4
781 | 2026-06-02 | D | 58 | CN002UD6982-3 | 003 | SW03 | ADHESIVE JOINT | SW | 4
782 | 2026-06-02 | D | 58 | CN002UD6982-3 | 003 | SW09 | ADHESIVE JOINT | SW | 4
783 | 2026-06-02 | FW | 58 | CN007UFW2375-2 | 002 | SW02 | ADHESIVE JOINT | SW | 12
784 | 2026-06-02 | FW | 58 | CN007UFW2375-3 | 003 | SW07 | LAMINATION | SW | 12
785 | 2026-06-02 | FW | 58 | CN007UFW2375-5 | 005 | SW05 | LAMINATION | SW | 12
786 | 2026-06-02 | D | 58 | CN002UD8669-1 | 001 | SW05 | LAMINATION | SW | 4
787 | 2026-06-02 | D | 58 | CN002UD8669-1 | 001 | SW09 | LAMINATION | SW | 4
788 | 2026-06-02 | D | 58 | CN006UD6693-4 | 004 | SW12 | LAMINATION | SW | 4
789 | 2026-06-03 | D | 58 | CN002UD8669-1 | 001 | SW07 | LAMINATION | SW | 4 | 8
790 | 2026-06-03 | D | 58 | CN006UD6693-4 | 004 | SW08 | LAMINATION | SW | 4
791 | 2026-06-03 | D | 58 | CN002UD6982-3 | 003 | SW01 | LAMINATION | SW | 4
792 | 2026-06-03 | D | 58 | CN002UD6982-3 | 003 | SW02 | LAMINATION | SW | 4
793 | 2026-06-03 | D | 58 | CN002UD6982-3 | 003 | SW03 | LAMINATION | SW | 4
794 | 2026-06-03 | D | 58 | CN002UD6982-3 | 003 | SW09 | LAMINATION | SW | 4
795 | 2026-06-03 | D | 58 | CN002UD6982-3 | 003 | SW10 | LAMINATION | SW | 4
796 | 2026-06-03 | FW | 58 | CN007UFW2375-2 | 002 | SW02 | LAMINATION | SW | 12
797 | 2026-06-03 | D | 58 | CN006UD6693-4 | 004 | SW14 | ADHESIVE JOINT | SW | 4
798 | 2026-06-03 | D | 58 | CN002UD6982-3 | 003 | SW02 | ADHESIVE JOINT | SW | 4
799 | 2026-06-03 | D | 58 | CN002UD6982-3 | 003 | SW05 | ADHESIVE JOINT | SW | 4
800 | 2026-06-03 | D | 58 | CN002UD6982-3 | 003 | SW07 | ADHESIVE JOINT | SW | 4
801 | 2026-06-03 | PW | 58 | CN006UPW1245-1 | 001 | SW01 | ADHESIVE JOINT | SW | 12
802 | 2026-06-03 | PW | 58 | CN006UPW1245-1 | 001 | SW04 | ADHESIVE JOINT | SW | 12
803 | 2026-06-04 | PW | 58 | CN006UPW1245-1 | 001 | SW01 | PARTIAL LAMINATION | SW | 12 | 9
804 | 2026-06-04 | PW | 58 | CN006UPW1245-1 | 001 | SW02 | PARTIAL LAMINATION | SW | 12
805 | 2026-06-04 | PW | 58 | CN006UPW1245-1 | 001 | SW04 | PARTIAL LAMINATION | SW | 12
806 | 2026-06-04 | PW | 58 | CN008UPW1245-1 | 001 | SW07 | PARTIAL LAMINATION | SW | 12
807 | 2026-06-04 | PW | 58 | CN006UPW1245-1 | 001 | SW02 | ADHESIVE JOINT | SW | 12
808 | 2026-06-04 | PW | 58 | CN008UPW1245-1 | 001 | SW07 | ADHESIVE JOINT | SW | 12
809 | 2026-06-05 | PW | 58 | CN006UPW1245-1 | 001 | SW01 | FINAL LAMINATION | SW | 12 | 5
810 | 2026-06-05 | PW | 58 | CN006UPW1245-1 | 001 | SW02 | FINAL LAMINATION | SW | 12
811 | 2026-06-05 | PW | 58 | CN006UPW1245-1 | 001 | SW04 | FINAL LAMINATION | SW | 12
812 | 2026-06-05 | PW | 58 | CN008UPW1245-1 | 001 | SW07 | FINAL LAMINATION | SW | 12
813 | 2026-06-06 | D | 58 | CN006UD6693-3 | 003 | SW14 | LAMINATION | SW | 4 | 9
814 | 2026-06-06 | D | 58 | CN006UD6693-4 | 004 | SW14 | LAMINATION | SW | 4
815 | 2026-06-06 | D | 58 | CN002UD6982-3 | 003 | SW05 | LAMINATION | SW | 4
816 | 2026-06-06 | D | 58 | CN002UD6982-3 | 003 | SW07 | LAMINATION | SW | 4
817 | 2026-06-06 | D | 58 | CN002UD6976-2 | 002 | SW04 | LAMINATION | SW | 4
818 | 2026-06-06 | D | 58 | CN002UD6982-1 | 001 | SW06 | LAMINATION | SW | 4
819 | 2026-06-06 | D | 58 | CN006UD8653-1 | 001 | SW03 | LAMINATION | SW | 4
820 | 2026-06-06 | FW | 58 | CN007UFW2375-4 | 004 | SW07 | ADHESIVE JOINT | SW | 12
821 | 2026-06-06 | FW | 58 | CN007UFW2375-4 | 004 | SW09 | ADHESIVE JOINT | SW | 12
822 | 2026-06-06 | D | 58 | CN002UD6976-2 | 002 | SW01 | ADHESIVE JOINT | SW | 4
823 | 2026-06-06 | D | 58 | CN002UD6976-2 | 002 | SW04 | ADHESIVE JOINT | SW | 4
824 | 2026-06-06 | D | 58 | CN002UD6976-1 | 001 | SW03 | ADHESIVE JOINT | SW | 4
825 | 2026-06-06 | D | 58 | CN002UD6976-1 | 001 | SW06 | ADHESIVE JOINT | SW | 4
826 | 2026-06-06 | D | 58 | CN002UD6982-1 | 001 | SW06 | ADHESIVE JOINT | SW | 4
827 | 2026-06-06 | D | 58 | CN006UD8653-1 | 001 | SW03 | ADHESIVE JOINT | SW | 4

## SUMMARY
SUMMARY |  |  | DETAILED SUMMARY
ABBREVATION | SUB SYSTEM | DIA INCH | SERVICE & JOINT SIZE | TOTAL DIA INCH | COMPLETED | PENDING
FW | FIRE WATER | 2238 | FW 4" | 52 | 40 | 12
|  |  | FW 6" | 138 | 60 | 78
DW | DISTILLED WATER / PORTABLE WATER | 195 | FW 8" | 320 | 176 | 144
|  |  | FW 12" | 1728 | 324 | 1404
PW | PRODUCED WATER | 240 | PW 12" | 240 | 48 | 192
|  |  | DW 2" | 12 | 0 | 12
D | DRAIN | 2224 | DW 3" | 183 | 0 | 183
|  |  | D 3" | 72 | 0 | 72
|  |  | D 4" | 2080 | 1012 | 1068
| TOTAL DIA INCH | 4897 | D 6" | 72 | 0 | 72
|  |  | AOC 20" | 320 | 120 | 200
|  |  | TOTAL | 5217 | 1780 | 3437

## AVAILABLE WORKFRONT
CPECC AVAILABLE WORK FRONT
SL.NO | ISOMETRIC DRW.NO | SERVICE | PIPE DIA | TOTAL JOINTS | COMPLETED JOINTS FIELD | TOTAL AVAILABLE JOINTS FIELD | COMPLETED JOINTS SHOP | TOTAL AVAILABLE JOINTS SHOP | TOTAL AVAILABLE DIA INCH
1 | CN001UD8648-1 | DRAIN | 4 | 8 | 0 | 4 | 4 | 4 | 32
2 | CN002UD6955-1 | DRAIN | 4 | 9 | 0 | 4 | 3 | 5 | 36
3 | CN002UD6955-2 | DRAIN | 4 | 9 | 0 | 4 | 4 | 5 | 36
4 | CN002UD6955-3 | DRAIN | 4 | 3 | 0 | 2 | 1 | 1 | 12
5 | CN002UD6955-4 | DRAIN | 4 | 2 | 0 | 0 | 2 | 2 | 8
6 | CN002UD6955-6 | DRAIN | 4 | 11 | 0 | 2 | 5 | 9 | 44
7 | CN002UD6965-1 | DRAIN | 4 | 23 | 0 | 4 | 15 | 19 | 92
8 | CN002UD6965-2 | DRAIN | 4 | 15 | 0 | 7 | 8 | 8 | 60
9 | CN002UD6976-2 | DRAIN | 4 | 0 | 0 |  | 1 |  | 0
10 | CN002UD6976-3 | DRAIN | 4 | 3 | 0 | 2 | 1 | 1 | 12
11 | CN002UD6976-4 | DRAIN | 4 | 6 | 0 | 3 | 3 | 3 | 24
12 | CN002UD6976-5 | DRAIN | 4 | 3 | 0 | 2 | 1 | 1 | 12
13 | CN002UD6976-6 | DRAIN | 4 | 8 | 0 | 4 | 4 | 4 | 32
14 | CN002UD6977-1 | DRAIN | 4 | 5 | 0 | 1 | 4 | 4 | 20
15 | CN002UD6982-1 | DRAIN | 4 |  | 0 |  | 1 |  | 0
16 | CN002UD6982-2 | DRAIN | 4 | 11 | 0 | 5 | 6 | 6 | 44
17 | CN002UD6982-3 | DRAIN | 4 | 0 | 0 |  | 7 |  | 0
18 | CN002UD8667-1 | DRAIN | 4 | 3 | 0 | 1 | 2 | 2 | 12
19 | CN002UD8669-1 | DRAIN | 4 | 0 | 0 |  | 3 |  | 0
20 | CN002UFW2375-4 | FW | 12 | 8 | 0 | 6 | 1 | 2 | 96
21 | CN002UFW2375-5 | FW | 12 | 8 | 0 | 3 | 3 | 5 | 96
22 | CN002UFW2442-1 | FW | 6 | 3 | 0 | 2 | 1 | 1 | 18
23 | CN002UFW2442-2 | FW | 6 | 4 | 0 | 1 | 3 | 3 | 24
24 | CN002UFW2447-1 | FW | 6 | 4 | 0 | 1 | 3 | 3 | 24
25 | CN002UFW2444-1 | FW | 8 | 4 | 0 | 1 | 3 | 3 | 32
26 | CN002UFW2457-1 | FW | 8 | 4 | 0 | 1 | 2 | 3 | 32
27 | CN006UD6674-1 | DRAIN | 4 | 8 | 0 | 3 | 5 | 5 | 32
28 | CN006UD6675-1 | DRAIN | 6 | 15 | 0 | 4 | 4 | 11 | 90
29 | CN006UD6675-2 | DRAIN | 4 | 16 | 0 | 7 | 8 | 9 | 64
30 | CN006UD6675-3 | DRAIN | 4 | 13 | 0 | 3 | 7 | 10 | 52
31 | CN006UD6675-4 | DRAIN | 4 | 18 | 0 | 7 | 5 | 11 | 72
32 | CN006UD6675-5 | DRAIN | 4 | 10 | 0 | 6 | 4 | 4 | 40
33 | CN006UD6675-6 | DRAIN | 4 | 4 | 0 | 2 | 2 | 2 | 16
34 | CN006UD6675-7 | DRAIN | 4 | 17 | 0 | 7 | 7 | 10 | 68
35 | CN006UD6675-8 | DRAIN | 4 | 11 | 0 | 5 | 6 | 6 | 44
36 | CN006UD6675-10 | DRAIN | 4 | 8 | 0 | 3 | 5 | 5 | 32
37 | CN006UD6675-11 | DRAIN | 4 | 17 | 0 | 7 | 8 | 10 | 68
38 | CN006UD6675-12 | DRAIN | 4 | 7 | 0 | 1 | 3 | 6 | 28
39 | CN006UD6675-13 | DRAIN | 4 | 17 | 0 | 7 | 9 | 10 | 68
40 | CN006UD6675-14 | DRAIN | 4 | 10 | 0 | 4 | 6 | 6 | 40
41 | CN006UD6683-1 | DRAIN | 4 | 8 | 0 | 3 | 2 | 5 | 32
42 | CN006UD6693-1 | DRAIN | 4 | 18 | 0 | 7 | 10 | 11 | 72
43 | CN006UD6693-2 | DRAIN | 4 | 14 | 0 | 5 | 6 | 9 | 56
44 | CN006UD6693-3 | DRAIN | 4 | 16 | 0 | 6 | 6 | 10 | 64
45 | CN006UD6693-4 | DRAIN | 4 | 15 | 0 | 5 | 3 | 10 | 60
46 | CN006UD6695-1 | DRAIN | 4 | 4 | 0 | 1 | 3 | 3 | 16
47 | CN006UD6696-1 | DRAIN | 4 | 6 | 0 | 1 | 4 | 5 | 24
48 | CN006UD6701-1 | DRAIN | 4 | 8 | 0 | 3 | 2 | 5 | 32
49 | CN006UD6705-1 | DRAIN | 4 | 13 | 0 | 6 | 7 | 7 | 52
50 | CN006UD6707-1 | DRAIN | 4 | 8 | 0 | 3 | 2 | 5 | 32
51 | CN006UD6743-1 | DRAIN | 4 | 10 | 0 | 2 | 6 | 8 | 40
52 | CN006UD6743-2 | DRAIN | 4 | 14 | 0 | 5 | 7 | 9 | 56
53 | CN006UD6743-3 | DRAIN | 4 | 18 | 0 | 6 | 7 | 12 | 72
54 | CN006UD6743-4 | DRAIN | 4 | 8 | 0 | 4 | 3 | 4 | 32
55 | CN006UD6747-1 | DRAIN | 4 | 20 | 0 | 14 | 4 | 6 | 80
56 | CN006UD6747-2 | DRAIN | 4 | 17 | 0 | 6 | 7 | 11 | 68
57 | CN006UD6765-1 | DRAIN | 4 | 8 | 0 | 3 | 1 | 5 | 32
58 | CN006UD6768-1 | DRAIN | 4 | 10 | 0 | 4 | 6 | 6 | 40
59 | CN006UD8649-1 | DRAIN | 4 | 6 | 0 | 1 | 4 | 5 | 24
60 | CN006UD8650-1 | DRAIN | 4 | 6 | 0 | 1 | 4 | 5 | 24
61 | CN006UD8653-1 | DRAIN | 4 | 6 | 0 | 1 | 1 | 5 | 24
62 | CN006UDW2148-1 | DRAIN | 4 | 13 | 0 | 6 | 0 | 7 | 52
63 | CN006UDW2148-2 | DRAIN | 4 | 12 | 0 | 6 | 0 | 6 | 48
64 | CN006UFW2361-1 | FW | 8 | 14 | 0 | 5 | 3 | 9 | 112
65 | CN006UFW2365-1 | FW | 6 | 4 | 0 | 1 | 0 | 3 | 24
66 | CN006UFW2366-1 | FW | 8 | 25 | 0 | 7 | 9 | 18 | 200
67 | CN006UFW2366-2 | FW | 8 | 17 | 0 | 8 | 5 | 9 | 136
68 | CN006UFW2366-3 | FW | 8 | 12 | 0 | 6 | 3 | 6 | 96
69 | CN006UFW2366-4 | FW | 8 | 19 | 0 | 9 | 6 | 10 | 152
70 | CN006UFW2525-1 | FW | 4 | 13 | 0 | 3 | 10 | 10 | 52
71 | CN006UPW1245-1 | PW | 12 | 10 | 0 | 5 | 3 | 5 | 120
72 | CN007UD6955-1 | DRAIN | 6 | 11 | 0 | 5 | 4 | 6 | 66
73 | CN007UD6955-2 | DRAIN | 4 | 7 | 0 | 4 | 0 | 3 | 28
74 | CN007UFW2375-2 | FW | 12 | 3 | 0 | 2 | 1 | 1 | 36
75 | CN007UFW2375-3 | FW | 12 | 11 | 0 | 6 | 2 | 5 | 132
76 | CN007UFW2375-4 | FW | 12 | 10 | 0 | 2 | 2 | 8 | 120
77 | CN007UFW2375-5 | FW | 12 | 8 | 0 | 3 | 1 | 5 | 96
78 | CN007UFW2375-6 | FW | 12 | 6 | 0 | 3 | 1 | 3 | 72
79 | CN007UFW2453-1 | FW | 4 | 4 | 0 | 1 | 3 | 3 | 16
80 | CN007UFW2457-1 | FW | 8 | 4 | 0 | 2 | 2 | 2 | 32
81 | CN007UFW2458-1 | FW | 8 | 6 | 0 | 1 | 3 | 5 | 48
82 | CN008UPW1245-1 | PW | 12 | 7 | 0 | 4 | 1 | 3 | 84
83 | 20'' | AOC | 20 | 16 | 6 | 16 | 0 | 0 | 320
84 | 14'' | AOC | 14 | 4 | 0 | 4 | 0 | 0 | 56
85 | 8'' | AOC | 8 | 83 | 0 | 83 | 0 | 0 | 664
| TOTAL |  |  | 877 | 6 | 405 | 324 | 472 | 5206
|  | TOTAL AVAILABLE WORKFRONT |  |  |  |  | 5206
|  | COMPLETED (DIA INCH) |  |  |  |  | 1780
|  | PENDING ( DIA INCH) |  |  |  |  | 3426
|  | NO. OF CREW AVAILABLE AT SITE |  |  |  |  | 1
|  | AVERAGE PRODUCTION PLANNED PER DAY |  |  |  |  | 60 / C
|  | PRODUCTION PLANNED PER WEEK |  |  |  |  | 360